## iTAMs
Actual Fix Date | Actual Fix Time | Adjustment End Date | Adjustment Start Date | Adjustment? | Application | Application Domain | Assigned To | Assigned To Full Name | Capability | Closed in Version | Closing Date | Comments | Conf Bridge Number | CQ_ID | Customer Impacts | Customer Impacts - Old | Cycle | Defect ID | Defect Type | Deployment Date | Description | Detected By | Detected By Full Name | Detected in Cycle | Detected in Release | Detected in Version | Detected on Date | Detected on Environment | Developer Assigned to Fix | eComms / PRM | EComms Impacts | Estimated Fix Date | Estimated Fix Time | Fix By | Function | Hot Fix | Impacted Test Case | Impacted Work Stream | Interface | IR Number | Issue Details | ITAM ID | ITAM Last Update | ITAM Link | ITAM Severity | ITAM Status | ITAM Updated | ITAM Work Info Details | Modified | Patch | Peer Reviewed By | PIR | Planned Closing Version | Preventative Action | Priority | PRM Impacts | Products | Project | RCA | Reason Status | Rejection/Deferral Reasons | Release / Production Code | Release Baseline | Release Recommendations | Report ID | Reproducible | Retest Blocked | Retest Failed Reason Code | Root Cause Analysis | Scenario Type | Severity | Solution Area | Solution Lead | SSL Assigned | SSL Assigned Full Name | Status | Sub Capability | Subject | Summary | Target Cycle | Target Release | Test Phase | Test Phase Stream | Test Phase Sub-Stream | Testing Due Date | Time Raised | Work Around
| 5 |  |  |  | CCB-PROD-CAT | Digital Markets - Digital Prod - Prodcat | john_mcbriarty |  |  |  | 8/28/2015 12:00:00 AM | Khamruz Zaman Syed - 24/08/2015 8:00:48 PM: As per ER1508 IR12131 change, a constraint rule is created to default the ' Apple Music 24 Month Trial Offer' for a user who has only CCB Offer Management Test and no CCB Offer Management BoH responsibility. The tester will need to remove the CCB Offer Management BoH responsibility and execute this scenario for this rule to fire. khamruz_syed Ph:9940050712 Email:khamruz.zaman@accenture.com ________________________________________ Khamruz Zaman Syed - 24/08/2015 8:01:13 PM: Assiging the defect to 'For Rejection'. khamruz_syed Ph:9940050712 Email:khamruz.zaman@accenture.com ________________________________________ Glen Conway - 25/08/2015 10:35:38 AM: Hi Please reference where this is documented. I have been testing the FUSE project in the past with a BVT users default profile and don't recall makin any profile changes. Which has Test &amp; BOH I have read through the PDD and BRD and the best I can find is that it should be available to BVT testing, I cant find anything on the defaulting for a TEST only profile This imitative will: · Ensure the Apple Music 24 Month Trial Offer is red (unelectable) and non-provisionable from 1508 (23/08/2015). The Apple Music 24 Month Trial Offershould be selectable for BVT users ONLY. · From the 05/09: o Apple Music 24 Month Trial Offer is selectable in Siebel across ALL CHANNELS o The Siebel rules (constraint and offer enforcement) which default the Apple Music 24 Month Trial Offer with eligible plans become active for ALL CHANNELS o The Siebel rules (constraint) which exclude the Apple Music 24 Month Trial Offer with ineligible plans become active for ALL CHANNELS glen_conway Ph:(03) 8647 5651 or 0413772449 Email:Glen.P.Conway@team.telstra.com; |  |  | Poor Customer Experience |  |  | 4101 | Configuration - Product |  | Test Set: SOC_Progression Test: [1]IR_12131_FUSE_ELIGIBILITY_TC03 Run: Run_8-24_12-38-16 Test Parameters: Failed at step 3 (In Red) Description: Pre-Condition ¿ Customer has never activated a FUSE product Step 1 ¿ Add New Mobile Service Step 2 ¿ Customise to add Go Mobile BYO Plan $70 (Eligible Plan) Step 3 - Which in tail adds the 24mth trial product, not the paid. Step 4 - Validate and Submit the order Step 5 - SMS should then get sent to remind the customer they are eligible. Step 6 - Create Modify order after the eligibility SMS is received to add the FUSE subscription, Validate and Submit the order Step 7 - Then once you add the paid, the ¿Welcome SMS¿ is received as per normal Expected Results: Step 1 - Order is created Step 2 - Customisation is successful Step 3 - Apple Music 24 Month Offer is defaulted Step 4 - Order is Valid Step 5 - SMS received Step 6 - Modify order created and submitted successfully Step 7 - FUSE Welcome SMS received Actual: 1-552846759770 | glen_conway |  |  |  |  | 8/24/2015 |  |  | eComms & PRM | Expecting the 24 Month FUSE offer defaults with an eligible plan, this is not occurring |  |  |  | Add New |  | IR_12131_FUSE_ELIGIBILITY_TC03 | Sales |  | 12131 | Test Parameters: Failed at step 3 (In Red) Description: Pre-Condition ¿ Customer has never activated a FUSE product Step 1 ¿ Add New Mobile Service Step 2 ¿ Customise to add Go Mobile BYO Plan $70 (Eligible Plan) Step 3 - Which in tail adds the 24mth trial product, not the paid. Step 4 - Validate and Submit the order Step 5 - SMS should then get sent to remind the customer they are eligible. Step 6 - Create Modify order after the eligibility SMS is received to add the FUSE subscription, Validate and Submit the order Step 7 - Then once you add the paid, the ¿Welcome SMS¿ is received as per normal Expected Results: Step 1 - Order is created Step 2 - Customisation is successful Step 3 - Apple Music 24 Month Offer is defaulted Step 4 - Order is Valid Step 5 - SMS received Step 6 - Modify order created and submitted successfully Step 7 - FUSE Welcome SMS received Actual: 1-552846759770 | INC000020108125 | 8/24/2015 12:55:06 PM | Y | 3 - Medium | Assigned | N |  | 3/29/2017 6:04:50 AM | [10 empty] | Failed |  | R1508_PCR1508 |  |  |  | Y |  |  |  | BVT Progression | 3 - Medium | Sales | Tamara Jansen | john_mcbriarty |  | Closed |  | BVT PROGRESSION | R1508_BVT_24 Month Offer Not Defaulting with Eligible Plan Selected via Offer Management Test Profile |  |  | 06 - BVT | CC&B - CRM |  |  | 8/24/2015 12:41:49 PM
[5 empty] | CCB-PROD-CAT | Digital Markets - Digital Prod - Prodcat | john_mcbriarty |  |  |  | 9/20/2015 12:00:00 AM | Udhayakumar Subramani - 25/08/2015 5:18:19 PM: As per the attached mail- This is expected behaviour. Assigning the defect 'For Rejection' udhayakumar_subramani Ph:9994613188 Email:u.subramani@accenture.com ________________________________________ Udhayakumar Subramani - 9/14/2015 11:38:23 PM: Hi Srinivasan, There is some more detailed update on incident INC000020109464. Please find below details. · Till 2nd Sep 2015 we need to default ADSL T-Gateway Kit. This is the requirement in ER1508 IR12048 KDD62A · As per the requirements in PCR1508 IR12983 we need to default the Gateway Max kits for all Large and X-Large core offers from 2nd Sep 2015 irrespective of access type selected · The order is created on or before 24th Aug 2015 (i.e. incident created date), so the ADSL T-Gateway Kit will be defaulted which is expected · From products configuration stand point we have below constraint rule which says for Copper Access Type as well, for Large and X-Large Core Offers we should default 'Telstra Gateway Max DSL/Fibre Kit' which will start on 2nd Sep 2015 · We have tested the similar scenario on 11th Sep 2015 in SIT3 and its working fine, i.e. Gateway Max Kit is getting defaulted · Can you ask BVT testing team to create order today and verify whether the expectation is aligned à Action on BVT Testing Team · Once we got confirmation from BVT testing team can you set the incident for Rejection Thanks Satish Rao udhayakumar_subramani Ph:9994613188 Email:u.subramani@accenture.com ________________________________________ Venkat Viswanathan - 17/09/2015 9:47:19 AM: Mail sent to Kieran and Closure process is being checked venkat_viswanathan Ph:919940525543 Email:venkat.viswanathan@accenture.com |  |  | None identified |  |  | 4102 |  |  | Source Data: Test Set: SoC Test: [1]Premierbundle_04 Run: Run_8-24_14-41-3 Test Parameters: Defect description: Gateway Max Modem is not defaulting when Ordering Premier Bundle from Dynamic Bundle Builder. as per KnowHow This is a free inclusion for all Premier Bundle customer Screen shots attached. Gateway Max was manually selected to allow order to progress as per expected results 1-553044022078 CAC: 2036226726 Steps to Reproduce: Actual Result: Fix Statement: Risk Assessment: | kieran_ives |  |  |  |  | 8/24/2015 | [7 empty] | Add New |  |  |  |  | 12048 |  | INC000020109464 | 8/24/2015 2:52:43 PM | Y | 3 - Medium | Assigned | N |  | 3/29/2017 6:04:50 AM | [12 empty] | R1508_PCR1508 |  |  |  | Y |  |  |  | BVT Progression | 3 - Medium | Sales | Tamara Jansen | john_mcbriarty |  | Rejected |  | DBB2 | IR12048_DBBBVT_Gateway Max is Not Defaulting for Premier Bundle Customers |  |  | 06 - BVT |  |  |  | 8/24/2015 2:41:51 PM
[5 empty] | CCB-PROD-CAT | Digital Markets - Digital Prod - Prodcat | john_mcbriarty |  |  |  | 9/20/2015 12:00:00 AM | Satish Rao - 15/09/2015 8:31:31 PM: 1. As part of PCR1504 IR12218 we have requirement to make the Telstra T-Box+ and T-Box+ Bundle Discount - 100% defaulted till 1st of Sep 2015 2. As part of ER1508 IR12048 KDD62A we have requirement to add all communication core offers to add to the rules created in PCR1504 IR12218 3. The Communication are shared across Communication Heros and Premier Heros. So till 1st of September for all Premier Hero offers selected Telstra T-Box+ and T-Box+ Bundle Discount - 100% will be defaulted. Which is expected. 4. From 2nd Sep 2015 onwards the configuration will be inactive and these products won't get defaulted. 5. We have tested in SIT3 and its working fine i.e. Telstra T-Box+ and T-Box+ Bundle Discount - 100% are not getting defaulted 6. Can we have BVT team to test the same scenario again and confirm us the results à Action on BVT team 7. We have attached the HLD documents of PCR1504 IR12218 and ER1508 IR12048 KDD62A for reference 8. Since the functionality is working as per requirement, can you please set this defect For Rejection satish_rao Ph:9884623231 Email:satish.rao@accenture.com ________________________________________ Venkat Viswanathan - 17/09/2015 9:47:37 AM: Mail sent to Kieran and Closure process is being checked venkat_viswanathan Ph:919940525543 Email:venkat.viswanathan@accenture.com |  |  | None identified |  |  | 4103 |  |  | Source Data: Test Set: SoC Test: [1]Premierbundle_04 Run: Run_8-24_14-57-44 Test Parameters: Defect description: Premier Bundle Originated form Dynamic Bundle Builder Is including T-Box as part of default Hardware which is not inline with KnowHow description of inlusions for this bundle Category, Order details are below. 1-553044022078 CAC: 2036226726 BAN:2000458438213 Steps to Reproduce: Actual Result: Fix Statement: Risk Assessment: | kieran_ives |  |  |  |  | 8/24/2015 | [7 empty] | Add New |  |  |  |  | 12048 |  | INC000020109819 | 8/24/2015 3:17:24 PM | Y | 3 - Medium | Assigned | N |  | 3/29/2017 6:04:50 AM | [12 empty] | R1508_PCR1508 |  |  |  | Y |  |  |  | BVT Progression | 3 - Medium | Sales | Tamara Jansen | john_mcbriarty |  | Rejected |  | DBB2 | IR12048_DBBBVT_Tbox defaulting for Premier Bundle Customers |  |  | 06 - BVT |  |  |  | 8/24/2015 2:58:44 PM
[5 empty] | CCB-RCRM | TSE - Customer Order Management & Sales | john_mcbriarty |  |  |  | 9/20/2015 12:00:00 AM | Venkat Viswanathan - 15/09/2015 10:15:34 AM: This is the expected behavior and Incident is closed for the same comments. venkat_viswanathan Ph:919940525543 Email:venkat.viswanathan@accenture.com ________________________________________ Venkat Viswanathan - 17/09/2015 9:47:57 AM: Mail sent to Kieran and Closure process is being checked venkat_viswanathan Ph:919940525543 Email:venkat.viswanathan@accenture.com |  |  | None identified |  |  | 4105 |  |  | Source Data: Test Set: SoC Test: [1]Premierbundle_04 Run: Run_8-25_11-26-36 Test Parameters: Defect description: when selecting an offer within the Dynamic Portal the name of that offer in the 'New Selection' Field presents twice, as per the attached this is a cosmetic issue only. Steps to Reproduce: Actual Result: Fix Statement: Risk Assessment: | kieran_ives |  |  |  |  | 8/25/2015 | [7 empty] | Modify |  |  |  |  | 12048 |  | INC000020116719 | 8/25/2015 12:01:58 PM | Y | 3 - Medium | Assigned | N |  | 9/18/2017 5:21:31 PM | [12 empty] | R1508_PCR1508 |  |  |  | Y |  |  |  | BVT Progression | 3 - Medium | Sales | Tamara Jansen | john_mcbriarty |  | Rejected |  | DBB2 | R1508_BVT_IR12048_Offer selection presents twice to User |  |  | 06 - BVT |  |  |  | 8/25/2015 11:26:41 AM
| 38 |  |  |  | CCB-RCRM | TSE - Customer Order Management & Sales | john_mcbriarty |  |  |  | 10/16/2015 12:00:00 AM | Mitesh Patel - 16/10/2015 3:03:44 PM: Please refer to the attached email in attachment which shows re-test has been successful. Defect can be close. mitesh_patel Ph:428029983 Email:mitishbhai.patel@team.telstra.com |  |  | Increased AHT;Others;Unknown |  |  | 4141 |  |  | Source Data: Test Set: SOC_Progression Test: [1]IR11389_BVT_TC02_PRM_CARE_Launch MAM Run: Run_9-9_14-42-13 Test Parameters: Step: Step 1 Description: Refer to BPVT Plan Expected Results: Refer to BPVT Plan Actual: User is directed away (to Media Portal Screen) from Siebel when clicking on Contacts Tab in PRM, Defect description: Steps to Reproduce: Actual Result: Fix Statement: Risk Assessment: | MANDEEP_SINGH |  |  |  |  | 9/09/2015 | [7 empty] | Customer Care |  |  |  |  | 11389 | User is getting directed away from Siebel when clicking on Contacts Tab in PRM | INC000020228266 | 9/09/2015 3:07:11 PM | Y | 3 - Medium | Assigned | N |  | 9/18/2017 5:21:32 PM | [12 empty] | R1508_PCR1508 |  |  |  | Y |  |  |  | BVT Progression | 3 - Medium | Sales | David Tucker | john_mcbriarty |  | Closed |  | BVT PROGRESSION | R1508_BVT_IR11389_ TC02_PRM_CARE_Launch MAM- User is directed away from Siebel when clicking on Contacts Tab in PRM |  |  | 06 - BVT |  |  |  | 9/09/2015 2:47:50 PM
| 14 |  |  |  | CCB-PROD-CAT | Digital Markets - Digital Prod - Prodcat | c673092 | McBriarty, John M |  |  | 9/04/2017 12:00:00 AM | Natarajan, Ishwariya [Accenture] - 22/8/2017 5:00:57 PM: We are looking into this. d749190 Ph: Email:ishwariya.natarajan@accenture.com ________________________________________ Natarajan, Ishwariya [Accenture] - 22/8/2017 11:32:47 PM: ***Comments from Tushar*** The plan defaulting is happening due to the configuration of PCD1707 IR16763. Below offers available in asset are expecting a plan to be selected as per rule which is correct. Offers : 4GB Mobile Data Share Bonus - Until Recontract 5GB Mobile Data Share Bonus - Until Recontract IR16763 Expectation: Multiple Mass Market Offers (Count = 2) can be selected only with below 4 plans. Go Mobile Plus Plan $95 Go Mobile Plus Plan $135 Go Mobile Swap Plan $95 Go Mobile Swap Plan $135 Next Action: 1. Please remove the above offers after entering econfigurator in the upgrade order & post that kindly select the new plan. This should not block other TCs. Please progress with testing. 2. Meantime, We are validating the business expectation for the IR16763 introduced in 1707. Please block one TC for this till we come up with the expectation & continue with other items. d749190 Ph: Email:ishwariya.natarajan@accenture.com ________________________________________ Soundarrajan, Gunasekaran [Accenture] - 08/23/2017 12:35:27 AM: Hi All, Changing the application to CCB-PROD-CAT since the QC is releated to Products d734155 Ph: Email:g.b.soundarrajan@accenture.com ________________________________________ Bhura, Rohit [Accenture] - 28/08/2017 11:51:59 AM: Awaiting Business (Alex Stavropoulos) view on this. d710870 Ph: Email:rohit.bhura@accenture.com ________________________________________ Bhura, Rohit [Accenture] - 30/08/2017 5:13:22 PM: Business has agreed to proceed with this behaviuor. Please find attached email for more details and take the QC for rejection. d710870 Ph: Email:rohit.bhura@accenture.com ________________________________________ Zhao, Borris - 4/09/2017 3:14:16 PM: FYI - orders now autodefaulting with Go Mobile Swap Plan $135 instead of previous Go Mobile Plus Plan $135 - refer to attachment d303606 Ph:+61 3 86475658 Email:borris.zhao@team.telstra.com ________________________________________ McBriarty, John M - 04/09/2017 5:03:08 PM: This was a valid test case that was signed off by the appropriate stakeholders. The test case failed. On investigation of this Defect it was subsequently found that no IT fixed was required and the business has agreed with the system beahviour. In this circumstance the Defect should be Closed not Rejected. c673092 Ph:+61 2 49181659 Email:john.mcbriarty@team.telstra.com |  |  | Increased AHT |  |  | 4831 |  |  | Test Set: SoC BVT Progression Test: IR15250_BVT_TC013_OUI_CRM - TSN EXPRESS_MODIFY REDEEM FROM GO MOBILE SWAP PLAN $95 TO GO MOBILE SWAP PLAN $75 WITH FREE EARLY HANDSET UPGRADE PROMOTION Run: Run_8-22_15-46-31 Test Parameters: Step: 1 Description: 1. Login to Siebel using TSN profile 2. Search for an existing customer on Go Mobile Swap plan $95 without Mobile Swap Assure 3. Create Upgrade mobile service order in Siebel Expres 4. Customise and add the following: - Go Mobile Swap plan $75 - any in-market DLC handset - Early handset upgrade promotion 5. Complete other mandatory fields and click Done. 6. A new Recontract Order Eligibility Screen will pop up. 7. Follow new strategic redemption process as per BAU 8. Complete the order as per BAU and submit Expected: 3. Order can be created successfully 4. Plans and handsets are added successfully 7. Redemption process successful 8. Order completes Actual: 2009144899 2000594383273 1-1249674452058 0400144606 as per word doc with screenshots, during mobile upgrade order to complete swap plan redemption, upon entering product configurator, Go Mobile Plus Plan $135 is auto defaulting incorrectly. Run Step[591445] : 1 | d303606 | Zhao, Borris |  |  |  | 8/22/2017 | [7 empty] | mobile upgrade |  |  |  |  | 15250 |  | INC000026253292 | 8/22/2017 4:10:16 PM | Y | 3 - Medium | Assigned | N |  | 9/04/2017 5:03:09 PM | [12 empty] | R1708_PCD1708 |  |  |  | Y |  |  |  |  | 3 - Medium | N/A | N/A | c673092 | McBriarty, John M | Closed |  | BVT PROGRESSION | 1708 - IR15250 - BVT - Mobile Upgrade Redeem order auto defaulting Go Mobile Plus $135 Plan |  |  | 06 - BVT |  |  |  | 8/22/2017 3:59:25 PM
| 2 |  |  |  | CCB-RCRM | TSE - Customer Order Management & Sales | c673092 | McBriarty, John M |  |  | 8/24/2017 12:00:00 AM |  |  |  | Order Cannot Be Completed |  |  | 4832 |  |  | Test Set: SoC BVT Progression Test: IR15858_TC12_SUPPORTTC_CHECKORDERLANDEDINSIEBEL_WS.8 Run: Run_8-23_9-49-5 Test Parameters: Step: Step 1 Description: Verify Order has flown through to Siebel after Subscriotion Purchase on handset Expected: Order has landed and completed Successfully in Siebel Actual: 1-1249410126589 - Order Failed Fulfilment Notification: ONENBR05(Do Not Sell in MICA) is mutually exclusive to ONENBR05(Do Not Sell in MICA) FMED-BUS-0024 Run Step[591347] : Step 1 | c920591 | Weerakoon, Bihan Y |  |  |  | 8/23/2017 | [7 empty] | Modiy Order |  |  |  |  | 15858 |  | INC000026258998 | 8/23/2017 10:09:04 AM | Y | 3 - Medium | Assigned | N |  | 9/18/2017 5:21:43 PM | [12 empty] | R1708_PCD1708 |  |  |  | Y |  |  |  |  | 3 - Medium | Sales | Nick Peacock | c673092 | McBriarty, John M | Closed |  | BVT PROGRESSION | IR15858 - Siebel EAI Order failed after Purchase of One Number Subscription via Handset |  |  | 06 - BVT |  |  |  | 8/23/2017 9:49:30 AM
| 11 |  |  |  | CCB-PROD-CAT | Digital Markets - Digital Prod - Prodcat | c673092 | McBriarty, John M |  |  | 9/04/2017 12:00:00 AM | Natarajan, Ishwariya [Accenture] - 27/8/2017 4:22:47 PM: We are looking into this. d749190 Ph: Email:ishwariya.natarajan@accenture.com ________________________________________ Natarajan, Ishwariya [Accenture] - 29/8/2017 3:43:19 PM: Hi Johnny Fix for the below issue is already packaged with PCD1709 and the same is available in SIT3 at the moment. The issue will be auto resolved post Go-Live of PCD1709.(Targeting 3rd Sep) Please let us know for any further queries on the same. Thanks Vishwa ATS Products Warranty/Fix +91 9600153377 d749190 Ph: Email:ishwariya.natarajan@accenture.com ________________________________________ Bhura, Rohit [Accenture] - 4/09/2017 2:59:30 PM: The fix has been been deployed as part of PCD1709 and available in Production now. Please take thsi for retest. d710870 Ph: Email:rohit.bhura@accenture.com ________________________________________ McBriarty, John M - 04/09/2017 3:09:41 PM: Mandeep Singh from Verification Testing team has confirmed that re-test has passed. Will now resolve this defect. c673092 Ph:+61 2 49181659 Email:john.mcbriarty@team.telstra.com |  |  | Others;Under Investigation;Unknown |  |  | 4836 |  |  | Test Set: SoC BVT Progression Test: IR16590_BVT_TC06_CRM - TESTING ACCESS_SUBMISSION_ADD NEW Run: Run_8-25_12-34-28 Test Parameters: Order ID: 1-1251317920985 BAN: 2000594593467 Step: 1 Description: 1. Login to Siebel using GCC Offer Management Testing profile 2. Create Add New mobile service order in Siebel Advance 3. Customise and add the following: - Go Mobile Plus BYO Plan $59 - International Calling Pack Discount (MDP0000033) 4. Complete the order as per BAU and submit Expected: 2. Order can be created successfully 3. Plan and handsets are added successfully- International Calling Pack Discount 4. Order completes Actual: 1-1251317920985 Run Step[591283] : 1 | d258318 | Singh, Mandeep |  |  |  | 8/25/2017 | [7 empty] | Add New |  |  |  |  | 16590 | R_PCD1708 – BVT_IR16590 – International Calling Pack Discount is showing as incompatible with Go Mobile Plus BYO plan $59. Error Message: Based on the existing compatibility and eligibility rules International Calling Pack Discount is not eligible: International Calling Pack Discount requires (via rule International Calling Pack Discount requires ). | INC000026279948 | 8/25/2017 12:58:02 PM | Y | 3 - Medium | Assigned | N |  | 9/04/2017 3:17:55 PM | [12 empty] | R1708_PCD1708 |  |  |  | Y |  |  |  |  | 3 - Medium | N/A | NA | c673092 | McBriarty, John M | Closed |  | BVT PROGRESSION | R_PCD1708 – BVT_IR16590 – International Calling Pack Discount is showing as incompatible with Go Mobile Plus BYO plan $59. |  |  | 06 - BVT |  |  |  | 8/25/2017 12:34:35 PM
| 21 |  |  |  | CCB-RBILL | TSE - BIOS - Billing | d344161 | Kodavatti, Chandrasekhar |  |  | 9/20/2017 12:00:00 AM |  |  |  | Others |  |  | 4838 |  |  | Test Set: GFS BVT Progression Test: R1708_BVT_IR15250_TC10_ Test case to verify the invoice and charges for the disconnect go mobile swap plan $135- customer keeps lease device Run: Run_8-31_10-5-30 Test Parameters: Run[87632] : Run_8-31_10-5-30 | d344161 | Kodavatti, Chandrasekhar |  |  |  | 8/31/2017 | [7 empty] | Evergreen |  |  |  |  | 15250 |  | INC000026248566 |  | N |  |  | N |  | 9/20/2017 12:10:54 PM | [12 empty] | R1708_PCD1708 |  |  |  | Y |  |  |  |  | 2 - High | Billing | Parmod | d344161 | Kodavatti, Chandrasekhar | Closed |  | IR15250 | R1708_IR15250_GFS BVT_Device Lease Contract is not taken into consideration during total MRO count calculation while performing Request Credit assessment |  |  | 06 - BVT |  |  |  | 8/31/2017 10:05:37 AM