## IR_Data
IR_Number | Release_Rollup | Title | IT_Project_Manager_Name | Description | Description_Of_Problem | Description_Of_Impact | Deployment_Category | Functional_Category | Test_Support_IR | State | Type | Category | DCP2_Funding | Indep_Requiring_CAT_Rls | RequirementsLead_fullname | EPM_Owner_fullname | IR_Actual_Cost | Business_Priority | Customer_Segments | Date_Required | Implemented_Date | IT_Project_Manager_Area | EPM_Project_Manager_Area | EPM_Proj_Manager_fullname | Date_Reqs_Received | Date_Reqs_Completed | Date_Solution_Completed | Date_Funding_In_Place | Date_Moved_to_IT_Endorsed | Date_Moved_to_Implemented | Requirements_Lead_Area | EPM_Owner_Area | Lead_Constructor | IT_Project_Manager.email
17226 | Indep | A.46055388 Evergreen Business B1a-(Dealer Commission)-MICA¦ TPOS Deployment | Chris Rowland | This IR is to track the next (and final) stage of deployment of MICA Product Configurations and T-POS for the parent IR 16503). | This IR is to track the next (and final) stage of deployment of MICA Product Configurations and T-POS for the parent IR 16503). | This IR is to track the next (and final) stage of deployment of MICA Product Configurations and T-POS for the parent IR 16503). |  | Products | No | Submitted | Agile | Cat-1 | No |  | Matthew Lew | Reid Johnson |  |  | Business | 2017-10-28 |  | Digital Markets - Digital Prod - ProjDeliveryER | Digital Markets - Digital Prod - ProjDeliveryER | Chris Rowland | 2017-05-17 | [5 empty] | Telstra Retail - Products/CMO | Telstra Retail - Products/CMO | Telstra Retail - Products/CMO | Chris.Rowland@team.telstra.com
33355 | R1702 | A.46022652 STOA Spillover | Priya Plutora | Capabilities to enable SIP Connect services to be deployed over non-NBN Telstra Broadband Accesses. The scope will be to enable the following: - Completion of LOLO-NBN functionality spilling over from R1611 | Business Broadband is a high growth product requiring enhancements to increase competitiveness and improve customer experience. | Completion of testing for functionality development for SIP Trunking over Broadband product. |  | Activation Assurance Billing & Credit Online Products | No | Solution | TDP | Cat-3A | No |  | Scarlett Lin | Crispin Blackall |  |  | Wholesale | 2017-02-12 |  | GB2B IT - Concept to Market & Mobility | TO - Networks | Barbara Matoe | 2016-10-03 |  | 2016-12-22 16:23 |  | 2016-12-23 09:26 |  | TO - Networks | GES - Global Products & Services | 2393689 | priyaplutora@gmail.com

## Financials
IR_NUMBER | DIRECTOR_ENDORSED_TOTAL
17158 | 0
17140 | 0
17024 | 0
17019 | 0
17018 | 0
17002 | 0
16977 | 0
16973 | 0
16966 | 0
16965 | 11878
16963 | 515267
16961 | 13343
16959 | 16272
16956 | 0
16955 | 548127
16954 | 0
16948 | 114971
16946 | 0
16944 | 26310
16941 | 0
16936 | 16807
16934 | 0
16926 | 30955
16923 | 0
16919 | 0
16910 | 28710
16901 | 14847
16897 | 104294
16882 | 17041
16851 | 48831
16836 | 231195
16796 | 132860
16792 | 63865
16790 | 47297
16782 | 20007
16778 | 11162
16759 | 17448
16758 | 15429
16757 | 127662
16750 | 205212
16730 | 0
16727 | 191327
16684 | 181643
16682 | 0
16677 | 333867
16665 | 600802
16640 | 8947483
16612 | 141223
16609 | 56711
16598 | 139897
16595 | 285133
16561 | 162720
16552 | 51908
16504 | 3693104
16503 | 215768
16487 | 2534623
16484 | 468390
16466 | 576030
16465 | 98610
16436 | 3580237
16400 | 501279
16360 | 1199541
16342 | 145680
16311 | 1359376
16301 | 1223761
16265 | 700930
16230 | 2403665
16207 | 593554
16130 | 1113428
16109 | 4234429
16101 | 279369
16069 | 949688
16046 | 2732311
16039 | 4491917
15913 | 192997
15882 | 1697949
15868 | 52163
15843 | 240300
15829 | 6158908
15781 | 5268853
15771 | 492729
15565 | 2426342
15068 | 1092250
14888 | 8312942
14771 | 5656602
14729 | 14176695
14600 | 1618038
14468 | 3799809
14436 | 612649
14234 | 0
14190 | 5428583
14151 | 74276

## BusinessDrivers
IR_Number | Business_Driver.Category_Type | Business_Driver.Description | Business_Driver.Planned_Date
17226 | Marketing / Business Event | This IR is to track the next (and final) stage of deployment of MICA Product Configurations and T-POS for the parent IR 16503). | 2017-11-07
17211 | Other | Product
17210 | Other | PCD
17209 | Revenue - Retained
17204 | Customer Satisfaction
17172 | Revenue - Incremental
17168 | Customer Satisfaction
17162 | Revenue - Incremental | Contractual obligation and service partner to NBN Co. | 2018-01-19
17159 | Operational Improvements | Background As a consequence of several nation-wide outages in early 2016, Telstra has undertaken a network architecture review, including the converged IMS (C-IMS) network. One of the outcomes of this review is the need to move from a single resource pool to a partitioned resource pool, hereafter referred to as “striping”. This move is in line with Telstra’s 2020 goal of creating network slices for different customer segments (LANES, consumers, IoT). In the process of creating these network stripes, additional network capacity must be installed. This additional capacity will for the most part consist of virtualised network functions (VNFs). This is also in line with Telstra’s goal of deploying Telco cloud to meet 5G network readiness. Why NFV Network Function Virtualisation (NFV) is an architectural framework for provisioning of compute, storage and network resources within a network. ETSI GS-NFV-002 outlines the main principles, ie. decoupling software from hardware flexible network function deployment dynamic operations (eg. Scaling) Ericsson’s NFV strategy is based on OPNFV (Open Platform for NFV) architecture and compliancy. Some of the key benefits of NFV are as follows Reduction in the amount of different O&M systems, interfaces and processed. (together with VNF workflows (note: a future roadmap item))allows process automation removing the need for manual work (eg. Capacity addition, function implementation) thus removing human error and giving faster TTM A common pool of hardware removes the need for peak capacity dimensioning for each separate function. When a large hardware pool is shared by all functions the scaling and energy efficiency is improved and OPEX is reduced.
17158 | Customer Satisfaction
17157 | Customer Satisfaction
17148 | Customer Satisfaction
17146 | Other | PCD Release
17145 | Operational Improvements
17140 | Legal/Regulatory Commitment | Need to maintain PCI compliance
17132 | Compliance with 3rd party | NBN Co will be offering this to all RSPs | 2017-08-25
17132 | Cost - Avoidance | Telstra will save $150 per new customer if we install the HFC modem on behalf of NBN Co | 2017-08-25
17131 | Efficiency
17128 | Legal/Regulatory Commitment
17127 | Efficiency
17124 | Customer Satisfaction | 1. The Customer Contact Management driver and falls under the Stream of work for ‘Reducing customer effort for when they need to contact us’; 2. It is part of the decision to scale a ‘One Touchpoint’ operating model; 3. A specifically addresses Component #1 ‘Multi-Channel Entry Point (Post-Order) which includes: 2-way SMS, Online, Live Chat, Email, and Voice (IVR); | 2017-10-20
17122 | Risk & Compliance | Non- compliances to Telstra's Information Security Standards means Telstra’s customer data could be exposed to malicious intent. Non-compliance to software currency
17122 | Other | Loss off automated tools used for code deployment, simplification of access request approval process from Vendors Loss of automated tools to query order status information tools to aid business and vendors with expediting analysis when resolving issues. Limitation to offshore vendors operational support capability to access CCB-RCRM without the need for onshore addition workaround
17121 | Business Launch Date | This initiative will: 1. Launch a new 3G Boost Mobile offer BOOSTX 2. Grandfather the BOOST28 offer 3. Build a tactical double data offer on recharge 31 Oct – 6 Feb 4. Launch a new $30 SIM Kit --- The purpose of this IR is to track the use of OSIT#3 environment only for related UAT ¦ Integration Testing for the IR. | 2017-10-31
17119 | Operational Improvements
17118 | Operational Improvements
17116 | Efficiency
17116 | Legal/Regulatory Commitment
17114 | Risk & Compliance
17110 | Operational Improvements | Gateway Consolidation 2 separate gateways to NBN Co currently in production will be consolidated in a unified B2B GW to NBN Co
17110 | Other | The project will consider the solution approach to migrate towards the strategic platform and solution, and opportunity to decommission the existing hardware platform (Ultimo P9). Objectives: - Reduce the risk of a significant business impact due to a catastrophic event in a "Risk Team -Top 45 apps", infrastructure or physical systems (e.g. data centre loss), aligned to Recovery Time/Point Objectives (MTPD, RTO, RPO). - Enable business continuity and address Group Audit findings (thereby reducing business and technology risk) - Protect Telstra revenue, profit & customer advocacy which are impacted by outages - Align the application remediation to an improvement in the CRS, through the remediation of key controls. B2BGW-NBN current CRS Lite score is 21 out of 30 (target is 18) - Determine the suitable solution option to mitigate against future service disruptions to B2BGW-NBN. | 2018-10-31
17109 | Efficiency | The IPDM solution will be an enabler of a number of business outcomes, namely: • Network Simplification • Network Virtualisation • Network as a Service (with APIs) • Network Convergence • Network Robustness. • Network Automation o Fulfilment (including Configuration) o Control o Assurance o Performance o Usage o Security o Analytical Operations However, to support the overall business drivers and directions of Telstra, network outcomes will also need to be supported by Operational outcomes. It is not within scope for the IPDM to determine operational readiness for the delivery of key business directions. However, there are some aspects of operational readiness which need to be integrated into the IPDM solution. | 2018-09-30
17108 | Operational Improvements | Without these changes, there is no way of easily identifying the workload for transition orders and hence no way that Telstra can adequately assign resources to complete the work in a timely manner. This is imperitive to keeping the customer satisfied, retaining revenue and maintaining a positive NPS score. | 2017-12-03 00:30
17102 | Customer Satisfaction |  | 2018-02-28
17102 | Business Launch Date |  | 2018-02-28
17079 | Revenue - Incremental
17077 | Operational Improvements | All Telstra Wholesale customers will receive an improved and standardised service removing a process that is manual and open to error and omission. | 2018-01-20
17076 | Other
17072 | Revenue - Incremental
17062 | Operational Improvements | Siebel runs faster on Chrome.
17061 | Efficiency
17055 | Customer Satisfaction | is to gracefully handle anticipated high ordering Cater to load on Foxtel Systems when they are supporting pre-identified high demand Main Events | 2017-12-02
17053 | Operational Improvements | This initiative will address the EoL s/w & h/w failures on the EAN and MSE Network (migration to SEP) for Ethernet Evolution topologies. | 2018-05-31
17051 | Customer Satisfaction
17048 | Business Launch Date | OOT capability deployments phase 1 | 2017-10-31
17048 | Business Launch Date | OOT capability phase 2 | 2017-11-14
17040 | Other | Products
17039 | Customer Satisfaction | Avoid Bill shock
17039 | Operational Improvements | Reduce billing errors
17039 | Revenue - Retained | Reduce / Remove undercharging for Biz Essentials bundles
17038 | Business Launch Date
17034 | Other | PCD Release
17033 | Other | PCD Release
17032 | Efficiency
17028 | Customer Satisfaction
17024 | Cost - Reduction | Fulfil USO obligations in a more cost effective manner
17022 | Cost - Reduction | Further reduce the unnecessary shipment of Gateways were a compatible gateway is already available at the customer's service. | 2018-02-18
17020 | Customer Satisfaction
17019 | Other | CAT1
17018 | Other | CAT1
17012 | Customer Satisfaction | Smooth provision of NBN orders for TB customers. With this change going into production , there will not be any need for manual workaround required for the impacted orders (176 orders as of 23rd Aug) .
17010 | Business Launch Date | CSM will be launching to the rest of Australia the PROMISE application at early Oct 2017 | 2017-10-13
17007 | Revenue - Retained
17005 | Customer Satisfaction
17005 | Revenue - Incremental
17002 | Operational Improvements | New functionality, performance improvements, configuration enhancements. Improved fraud detection algorithms in order to address increasing complexity and volumes of data sources. | 2018-03-03
17001 | Business Launch Date
17000 | Legal/Regulatory Commitment | The ACCC has developed new guidelines on the naming of NBN speeds to better align the naming with customer expectations. Update speed boost naming to align with ACCC guidelines and associated Data Conversions. | 2017-10-29
16998 | Existing Capability | Include self service of Data Bank in Online Channels | 2018-02-28
16997 | Legal/Regulatory Commitment | 1) Existing Required Cabling Solution only captures FTTP Voice Only Migration Orders in the EFCC Report. 2) Existing RCS and EFCC Report does not have the ""Installation Type"" details.
16995 | Revenue - Retained | A Do-Nothing scenario will see this figure grow to >$10M dollars in lost revenue for Telstra by end October 2017 This is significant and will continue to grow to > $12M by the start of 2018
16994 | Business Launch Date
16994 | Business Launch Date | Remove vulnerable end-of-life routers from the TID network. This will be achieved by migrating their functions onto existing routers that do not have that vulnerability, and installing new equipment where there is not enough capacity on the existing infrastructure
16993 | Revenue - Incremental
16992 | Other | Products
16989 | Business Launch Date |  | 2017-11-30
16982 | Legal/Regulatory Commitment
16980 | Operational Improvements
16978 | Operational Improvements | Case manager will be become more productive by using the automation and the enhancements
16977 | Other | CAT1 PCD
16975 | Other | Products
16974 | Other | Products
16973 | Revenue - Incremental
16972 | Operational Improvements | Higher speed would allow easier navigation across the screens in the contact centers. This would allow for less waiting time and better service to the customers. | 2017-10-04
16971 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC
16966 | Other | CAT1 PCD
16965 | Other | PCD release
16963 | Efficiency
16962 | Customer Satisfaction | Enable our FOH agent access the FFT information to serve them better | 2018-04-16
16961 | Other | PCD release
16959 | Other | PCD release
16957 | Customer Satisfaction
16956 | Other | CAT1
16955 | Efficiency
16954 | Other | PCD Release
16953 | Cost - Reduction
16953 | Customer Satisfaction | Address key drivers of poor NPS through the following: •Less time and reduced effort •Reduced complaints and customer dissatisfaction
16952 | Existing Capability | To address the immediate concern associated with the unsupported critical marketing software (IBM Suite) and capacity issues and to ensure that current direct Telstra retail marketing operations continue uninterrupted.
16949 | Efficiency
16949 | Operational Improvements
16948 | Cost - Avoidance | If NBN order volumes go to voice rather than email/SMS costs will increase | 2017-09-29
16948 | Customer Satisfaction | If customers receive calls or have to talk to Call centre staff when they otherwise could have received an SMS or email they will be less satisfied. | 2017-09-29
16946 | Legal/Regulatory Commitment | Need to maintain compliance
16945 | Other | Product
16944 | Existing Capability | Renwal of B2B-VIVA certificates
16943 | Cost - Avoidance
16943 | Customer Satisfaction
16943 | Cost - Reduction
16941 | Other | Product
16939 | Revenue - Incremental | Revenue generation for new business | 2018-02-28
16936 | Other | PCD Release
16935 | Legal/Regulatory Commitment
16934 | Other | CAT1 PCD
16933 | Operational Improvements | update to existing interface | 2017-08-24
16930 | Other | PCD Release
16926 | Other | PCD Release
16923 | Efficiency
16919 | Other | PCD Release
16915 | Customer Satisfaction
16915 | Efficiency
16915 | Operational Improvements
16915 | Legal/Regulatory Commitment
16911 | Risk & Compliance | To ensure risks involved in manual handing of data is removed.
16910 | Other | PCD Release
16909 | Customer Satisfaction
16906 | Revenue - Incremental
16902 | Revenue - Incremental | new business stream
16901 | Other | PCD Release
16900 | Efficiency | Current 10G arrangements are unable to scale in an efficient and cost effective manner. This project is driven by the need to deliver a more cost effective solution. | 2018-02-02
16899 | Customer Satisfaction
16899 | Operational Improvements
16899 | Cost - Reduction
16899 | Cost - Avoidance
16898 | Other | Superior mass market fulfilment customer experience Customer Experience: Right device to right customer at the right time Cost Efficiency: Cost reduction for Retail Supply Chain Future Flexibility: Partner with any supplier | 2018-06-10
16897 | Business Launch Date |  | 2017-09-17
16896 | Customer Satisfaction
16892 | Customer Satisfaction | Reduce first bill shock
16890 | Existing Capability | Enhancement to existing capability in OSS IT Systems to support the new DWDM based transport solution for Belong | 2018-02-03
16885 | Customer Satisfaction
16883 | Operational Improvements
16882 | Other | PCD Release
16880 | Revenue - Incremental
16878 | Customer Satisfaction | • 2 days’ time reduction in capturing the serial number updates. • Easy tracking
16878 | Cost - Reduction | Savings on the TTV hardware where customers choose not to Opt in
16877 | Operational Improvements
16872 | Legal/Regulatory Commitment
16870 | Existing Capability | Enable HNG devices to be continued to be dispatched
16869 | Operational Improvements | Remediate slow response
16865 | Business Launch Date
16862 | Customer Satisfaction
16862 | Efficiency
16851 | Other | PCD Release
16847 | Business Launch Date
16845 | Customer Satisfaction
16845 | Cost - Avoidance
16841 | Other | Exit PSTN/ Improve Number search and Reservation (Geographic Number Portability
16838 | Revenue - Retained
16838 | Customer Satisfaction
16836 | Customer Satisfaction | Case managers will be more empowered with this tool and with the reduction in AHT, this will improve Telstras NPS
16836 | Operational Improvements | Reducing AHT in the form of providing the right information when required and not having to swivel chair
16834 | Business Launch Date
16830 | Efficiency
16827 | Cost - Reduction | Customer self service will reduce FOH and BOH interactions | 2017-12-02
16827 | Customer Satisfaction | Customer Self Service allows customers to perform appointment reschedules at the time of their choosing and without going through the call centre experience | 2017-12-02
16820 | Efficiency
16818 | Cost - Reduction
16817 | Risk & Compliance
16817 | Customer Satisfaction
16816 | Existing Capability
16812 | Other | Development of base capability. | 2018-01-31
16809 | Efficiency | Reduce Swivel Chair
16808 | Customer Satisfaction
16808 | Revenue - Retained
16804 | Risk & Compliance
16804 | Customer Satisfaction
16803 | Customer Satisfaction
16802 | Customer Satisfaction | Allow customers to launch their own password reset / retrieval from Smart Help.
16801 | Risk & Compliance
16796 | Customer Satisfaction
16795 | Operational Improvements
16792 | Operational Improvements | Reduction in support incidents and improvement in opportunity lifecycle time. achieved by keeping Maxim and Sentient in synch more regularly. | 2018-01-12
16790 | Other | PCD Release
16789 | Customer Satisfaction | reduces the first Bill shock
16782 | Other | PCD Release
16780 | Risk & Compliance
16780 | Operational Improvements
16780 | Customer Satisfaction
16778 | Other | PCD Release
16774 | Risk & Compliance | Application Decommissioning | 2018-06-30
16773 | Existing Capability | Replacing C-IMS EMA with Mediator | 2017-09-30
16772 | Risk & Compliance | Application Decommissioning | 2018-06-30
16770 | Risk & Compliance | Application Decommissioning | 2018-06-30
16767 | Business Launch Date
16766 | Efficiency
16765 | Efficiency
16764 | Business Launch Date
16759 | Other | PCD Release
16758 | Other | PCD Admin IR
16757 | Other | PCD Admin IR
16751 | Operational Improvements | Delivering new products on new strategic IT stack.
16750 | Business Launch Date |  | 2017-11-14
16747 | Customer Satisfaction
16730 | Customer Satisfaction | Case managers will be more empowered with this tool and with the reduction in AHT, this will improve Telstras NPS
16730 | Operational Improvements | Reducing AHT in the form of providing the right information when required and not having to swivel chair
16727 | Legal/Regulatory Commitment
16714 | Customer Satisfaction | A higher success rate of the delivery of customer equipment is needed.
16711 | Operational Improvements
16709 | Cost - Avoidance | Protect Telstra revenue, profit & customer advocacy which are impacted by outages
16709 | Revenue - Retained | Protect Telstra revenue, profit & customer advocacy which are impacted by outages Enable continuity in the event of a catastrophic incident at the primary site.
16705 | Revenue - Incremental | Drive growth in incremental revenue | 2018-05-01
16705 | Business Launch Date | 2018-05-01 | 2018-05-01
16705 | Customer Satisfaction | Change in customer behaviour & growth in mobile data Increasing competitive landscape in Australia | 2018-05-01
16704 | Business Launch Date |  | 2017-09-05
16703 | Risk & Compliance | Risk with incorrect customer and contact Data
16702 | Operational Improvements | The new order type for relocations, and automated mobile provisioning means a more streamlined O2A process.
16702 | Customer Satisfaction | Faster provisioning times with less chance of error means higher Customer satisfaction.
16698 | Customer Satisfaction
16697 | Legal/Regulatory Commitment | nbn
16695 | Legal/Regulatory Commitment |  | 2017-08-31
16693 | Legal/Regulatory Commitment | PCI-DSS compliance requirements
16687 | Cost - Reduction | Reducing BDE
16684 | Business Launch Date | Requirem,ents and solution are a must for product launch | 2017-10-02
16684 | Customer Satisfaction | Customer Satisfaction Changes that are seen as essential to customer satisfaction and solution
16682 | Operational Improvements
16677 | Customer Satisfaction
16677 | Operational Improvements
16666 | Cost - Avoidance | Introduce Self Install option for NBN Telstra business customers, removing the need for CT to attend the majority of new connects/transitions
16666 | Customer Satisfaction | Minimise failed truck rolls/Telstra appointments
16665 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC (Fibre to the curb)
16660 | Other | product
16653 | Operational Improvements
16649 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC.
16647 | Customer Satisfaction
16646 | Customer Satisfaction
16644 | Legal/Regulatory Commitment
16644 | Operational Improvements
16640 | Operational Improvements
16640 | Efficiency
16636 | Other | Providing reference data capability and improved structures for new initiatives
16630 | Operational Improvements | New functionality, performance improvements, configuration enhancements. Improved fraud detection algorithms in order to address increasing complexity and volumes of data sources.
16627 | Other | Replace EMA - part of PSTN Exit
16622 | Legal/Regulatory Commitment
16616 | Customer Satisfaction
16615 | Efficiency
16612 | Compliance with 3rd party | Install 3rd party Oracle DB patch. | 2017-07-29
16609 | Other | PCD Release
16607 | Operational Improvements | BPVAS is reaching its end of life and is tracking to be decommissioned.
16606 | Operational Improvements | BPVAS platform is reaching its end of life.
16605 | Customer Satisfaction
16605 | Risk & Compliance
16605 | Efficiency
16600 | Customer Satisfaction
16598 | Cost - Reduction
16598 | Customer Satisfaction
16595 | Customer Satisfaction | Faster registration process thus resulting in customer satisfaction.
16595 | Efficiency | Automated process allows customers to do their own online move orders .
16594 | Operational Improvements | Minimise risk of compromising passwords on clear text and simplifying the process | 2018-04-30
16586 | Other | Superior mass market fulfilment customer experience Customer Experience: Right device to right customer at the right time Cost Efficiency: Cost reduction for Retail Supply Chain Future Flexibility: Partner with any supplier | 2018-03-31
16579 | Operational Improvements | This initiative will address the EoL s/w & h/w failures on the EAN and MSE Network (migration to SEP) for all requested Mobiles and Ethernet Evolution topologies. | 2018-05-31
16578 | Revenue - Incremental | Telstra to perform field work for NBN Co as part of OMMA agreement as a Service Delivery Partner
16574 | Business Launch Date | Requirement are a must have for product launch
16574 | Customer Satisfaction | Customer Satisfaction Changes that are seen as essential to customer satisfaction or solution
16561 | Efficiency
16553 | Operational Improvements
16552 | Efficiency | RCRM / RPRM OUI should work similar to HI while minimising the screen & in small monitors and shouldn't cause any resizing issues.
16549 | Legal/Regulatory Commitment | SSU Compliance to separate wholesale and retail
16546 | Operational Improvements | Provides ubiquitous scale (100G moving to 400G circuits) Improved transmission resiliency (dynamic wavelength switching). Enables the Core IP network design to be more efficient.
16541 | Business Launch Date | Production IT deployment scheduled for 1 week before to allow BVT activities. | 2017-09-04
16538 | Operational Improvements | To avoid the risk of Network failure events, while Fixed Broadband traffic growth exceeding forecast. | 2018-03-05
16512 | Revenue - Incremental
16509 | Operational Improvements | Centralised Usage Platform project objectives are to consolidate regionalised and centralised POP data stores into a virtualised and centralised usage platform as part of a technology refresh to a NoSQL architecture supporting Development Operation processes. | 2018-06-29
16506 | Other | Consultancy
16504 | Revenue - Incremental
16503 | Revenue - Incremental
16498 | Cost - Reduction | Recent series of incidents has impacted the BPVAS platform, especially around identity due to capacity issues. Completion of this project will provide a higher degree of network resilience and improved network performance.
16497 | Cost - Reduction | Recent series of incidents has impacted the BPVAS platform, especially around identity due to capacity issues. Completion of this project will provide a higher degree of network resilience and improved network performance.
16496 | Cost - Reduction | Recent series of incidents has impacted the BPVAS platform, especially around identity due to capacity issues. Completion of this project will provide a higher degree of network resilience and improved network performance.
16487 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC (Fibre to the curb)
16486 | Legal/Regulatory Commitment | DA agreement with nbn
16484 | Customer Satisfaction | Improves NPS by 30 points as customers call raise service request at their convenience
16484 | Cost - Reduction | Reduces calls to GCC and helps reduce GCC staffing costs.
16467 | Customer Satisfaction
16466 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC.
16465 | Revenue - Incremental | Telstra to perform field work for NBN Co as part of OMMA agreement as a Service Delivery Partner
16462 | Operational Improvements | This initiative will prevent the mistreatment of GES accounts that are in Seibel. | 2017-09-24
16457 | Cost - Reduction
16457 | Customer Satisfaction
16450 | Business Launch Date |  | 2017-11-30
16447 | Customer Satisfaction |  | 2017-10-29
16443 | Cost - Reduction | Reduce operational costs by using lower cost contact channels | 2017-11-30
16443 | Revenue - Retained | Reduce invoice days outstanding by selecting the most effective contact channel for the customer | 2017-11-30
16436 | Cost - Avoidance
16436 | Cost - Reduction
16436 | Customer Satisfaction
16435 | Customer Satisfaction | Increased customer experience due to cost savings and convenience.
16433 | Risk & Compliance | In Dec 2014 Telstra signed revised Definitive Agreements with NBN Co and the Common Wealth to enable to rollout of the Government’s Multi Technology Mix (MTM) national Broadband Network (NBN). The MTM Rollout includes the rollout of a Fibre to the Node (FTTN), & FTTC (Fibre to the curb)
16431 | Cost - Reduction | Reduce costs in TOPs by reducing faults received by phone.
16431 | Customer Satisfaction | Satisfy customer requests to introduce Case Create and CVA feedback to reduce effort in raising faults.
16431 | Operational Improvements | Simplification of customer contact centre staff on-boarding, induction and training processes; greater operating efficiency through faster data entry (no need to establish & re-establish LOLS session), and reduced phone calls to log faults.
16431 | Revenue - Incremental | Increase take up of existing LOLS Integrated™
16430 | Customer Satisfaction | Customer rebate is credited on time. | 2017-07-31
16430 | Revenue - Retained | Customer does not churn due to dissatisfaction with Telstra. | 2017-07-31
16427 | Cost - Reduction
16427 | Efficiency
16416 | Customer Satisfaction
16414 | Cost - Reduction | Email bills to customers instead of print/post bills
16414 | Marketing / Business Event | Customer communications via emails (promotional, marketing, welcome letter, notifications, alerts)
16414 | Customer Satisfaction | Customers have raised complaints to Telstra for the lack of email bill capability.
16400 | Customer Satisfaction
16391 | Risk & Compliance | Application Decommission | 2018-06-30
16390 | Revenue - Incremental
16386 | Cost - Avoidance
16386 | Operational Improvements
16381 | Business Launch Date | Business Launch date 1 May 2018 | 2018-05-01
16381 | Customer Satisfaction | Change in customer behaviour & growth in mobile data Increasing competitive landscape in Australia
16381 | Revenue - Incremental | Drive growth in incremental revenue
16379 | Business Launch Date | 2018-05-01 | 2018-05-01
16379 | Customer Satisfaction | Change in customer behaviour & growth in mobile data Increasing competitive landscape in Australia
16379 | Revenue - Incremental | Drive growth in incremental revenue
16378 | Operational Improvements | • Migration of WIP domains into SEP architecture • Support new IPMAN/EMAN service growth on SEP including interworking with WIP21/22. • GWIP Services – Long haul
16363 | Customer Satisfaction
16363 | Efficiency
16360 | Customer Satisfaction
16360 | Revenue - Retained
16342 | Operational Improvements
16342 | Revenue - Retained
16339 | Compliance with 3rd party | Telstra has agreed with Foxtel to support their Satellite first strategy. | 2017-09-03
16322 | Efficiency
16313 | Customer Satisfaction
16311 | Efficiency
16311 | Cost - Reduction
16311 | Customer Satisfaction
16306 | Other | Enable agents real time access top customer information
16305 | Customer Satisfaction | Foxtel from Telstra customers will now have an online self service capability similar to that provided by Foxtel to the Foxtel direct customers
16301 | Revenue - Retained | Ethernet Access Over NBN TC-2 is a project to build a ‘go to’ product to replace Telstra Wholesale Ethernet Access (copper), BDAS (Liteand Standard) and TW BDSL. These products are all affected by NBN Co’sWhite Paper number 1. Mandatory disconnection of these products
16289 | Customer Satisfaction
16289 | Efficiency
16281 | Cost - Avoidance | The current terradata platform is at end of life and would need significant financial outlay to upgrade | 2017-09-29
16281 | Efficiency | Alignment to Cloud First strategy
16274 | Customer Satisfaction
16272 | Other | Speed to market and new way of working
16265 | Revenue - Retained | Ethernet Access Over NBN TC-2 is a project to build a ‘go to’ product to replace Telstra Wholesale Ethernet Access (copper), BDAS (Liteand Standard) and TW BDSL. These products are all affected by NBN Co’sWhite Paper number 1. Mandatory disconnection of these products in NBN Ready For Service areas will commence on 12 Nov 2018. The project is aiming to present a Gate 3 Business Case by 5 April to meet ER1708 entry. Aiming to launch the product at the end of October 2017.
16243 | Other | NRL rights agreement changes from 2018 season onward leaving NRL mobile apps and live game streaming as the only digital components to be managed by Telstra.
16240 | Risk & Compliance | Enable business resilience and disaster recovery capability- make the TCM and TCM-EAI applications more resilient; the alternate infrastructure will be set up at a Disaster Recovery site. | 2017-10-18
16240 | Operational Improvements | Upgrade the software version of the TCM application from 8.1.1.4, to IP16 (Siebel Innovation Pack 2016); a major upgrade of Siebel. | 2017-10-18
16240 | Operational Improvements | Support connectivity of software components via the Telstra TIBCO EMS-BB where the JMS transport protocol is utilised. | 2017-10-18
16240 | Operational Improvements | Upgrade the TIBCO BusinessWorks software version of the TCM application from 5.7.1 to 5.12. | 2017-10-18
16240 | Cost - Avoidance | Operating expense reduction and ongoing capital efficiencies – Reduce operational costs by shrinking data centre footprint while increasing capacity and reducing environmental impacts. | 2017-11-24
16240 | Operational Improvements | Reduce technological risk to the transactions and to the business. | 2017-10-18
16232 | Other | Software upgrade
16230 | Customer Satisfaction
16207 | Operational Improvements | to provide BAU functionality of engaging TSO supporting all the existing scenarios from SIIAM and Siebel CSA. This handoff’s capability is intended to be of general use by all consumers to create incidents on ITAM. | 2017-08-31
16202 | Revenue - Incremental
16193 | Operational Improvements | The objective of the Product and Platform simplification (PPS) and Resilience program of work is to simplify the complexity of Telstra’s infrastructure environment and its operations. This includes: migrating applications from legacy infrastructure to modern simplified infrastructure platforms (EPIC), upgrading the software currency to the latest SOE version, replacing non SOE software with SOE alternatives, enhancing Disaster recovery capability, and boosting application availability.
16192 | Cost - Reduction | Avoid cost of either double developing bundles in legacy and consumer systems
16192 | Revenue - Incremental | Consumer mobile data products developed on OCS cannot be sold across to TB/GES.
16185 | Legal/Regulatory Commitment | Continue to fulfil obligations to nbn
16175 | Efficiency
16175 | Operational Improvements
16175 | Other | Incremental Customer Risk Score reduction over the duration of the program
16131 | Customer Satisfaction | The BPVAS and UBER platforms host critical Telstra applications and are ‘end of life’ and facing difficulties in meeting resource and capacity demands. The migration to TOP should provide the much needed resources for the application
16130 | Customer Satisfaction | The BPVAS is running out of resources. Lack of resources could cause problems to access the application. ACG is a critical application within Telstra Digital infrastructure
16119 | Customer Satisfaction | Improved delivery timeframe for MOVE orders. Fitter and Faster have identified that this is important and will have a big improvement to NPS
16114 | Operational Improvements | Improve SPARC platform resiliency while at the same time reducing operational costs significantly | 2017-06-30
16113 | Customer Satisfaction
16113 | Cost - Reduction
16109 | Risk & Compliance
16107 | Compliance with 3rd party | Autodesk Licensing Breach: The breach of ETR (extra terrestrial rights) was incurred inadvertently with offshoring to Philippines and India. | 2018-02-28
16101 | Customer Satisfaction | Increase the number of customer activations per month
16101 | Revenue - Incremental
16094 | Customer Satisfaction | There is an opportunity to promote Telstra’s leadership in NBN performance by delivering transparent and reliable information to our customers during pre-sale, point of sale and once connected, about the line speed experience they should expect.
16078 | Efficiency
16078 | Operational Improvements
16078 | Other
16077 | Risk & Compliance | Compliant to NBN
16069 | Cost - Reduction | Decommissioning ECHIDNA will remove ECHIDNA support costs
16069 | Risk & Compliance | ECHIDNA is currently in a “lock-down” in terms of new development. Only reference data changes can be made to ECHDINA commissions, no new development is allowed. This means that we cannot support any change to the current commission formulas – this restricts the ability of business to change the way they incentivise partners.
16069 | Compliance with 3rd party | ECHIDNA only supports Monthly commission calculation which means that Dealers can't be paid within 30 days for some commission calculations. Once functionality is migrated to CCB-COMM, weekly payment cycles will be supported which will enable Dealers to be paid within 30 days as promised by Andy Penn.
16069 | Risk & Compliance | ECHIDNA is running on old versions of HP-UX/ LINUX / Oracle DB which are no longer properly supported by the third party Vendors.
16060 | Operational Improvements
16056 | Risk & Compliance | Aging hardware - replatform required to minimise risk of failure
16046 | Cost - Reduction | Contributes to ability to decommission the UBER/BPVAS platform, therefore reducing cost of maintaining a legacy platform. | 2017-05-16
16039 | Operational Improvements | The objective of the Product and Platform simplification (PPS) and Resilience program of work is to simplify the complexity of Telstra’s infrastructure environment and its operations. This includes: migrating applications from legacy infrastructure to modern simplified infrastructure platforms (EPIC), upgrading the software currency to the latest SOE version, replacing non SOE software with SOE alternatives, enhancing Disaster recovery capability, and
16006 | Other | Exit PSTN
16005 | Cost - Reduction | Introducing virtualisation to reduce expenditure on physical infrastructure.
15945 | Customer Satisfaction
15945 | Revenue - Incremental
15944 | Risk & Compliance | Legacy SAM is on out of date software, and is due to be retired concurrent with the retirement of the legacy Ethernet networks it supports | 2017-06-23
15937 | Cost - Reduction
15923 | Customer Satisfaction
15915 | Other | Enable agents real time access to TB information
15913 | Business Launch Date | On-board partners with carrier billing capabilities. | 2017-04-27
15882 | Revenue - Incremental | enable revenew for BigDAta program of $700M in 3 years
15868 | Other | Historically our managed services solution has been outsourced and has focused on device and fleet management, with some application management and expense management. In July 2017, we purchased MSC Mobility (now BTS Mobility) our core managed services partner to deliver our managed services inhouse. None of our domestic competitors currently offer a service with EMaaS’ breadth. To do so they would need to partner with other providers. In Australia, the enterprise mobility market is forecast to grow from $3.8bn to $6.3bn between 2014 and 2020. However, while the Connectivity segment is forecast to be flat during this period, Apps and Content, Professional & Managed Services (Services), and Platforms segments are forecast to grow at 22% CAGR. Similarly, in Asia (incl. Australia), Apps & Content, Services, and Platforms drive most of the forecast growth to 2020 at 22% CAGR. EMaaS is critical for increasing both our attachment rate (~8% GES, 0.5% TB) and our $15 ARPU | 2017-01-11
15843 | Legal/Regulatory Commitment
15843 | Operational Improvements
15832 | Other | Alignment with Cloud first IT Strategy
15829 | Cost - Avoidance | Telstra will save $150 per new customer if we install the HFC modem on behalf of NBN Co | 2017-08-25
15829 | Compliance with 3rd party | NBN Co will be offering this to all RSPs | 2017-08-25
15800 | Efficiency
15800 | Legal/Regulatory Commitment
15793 | Other | To monitor the alignment of BDC Salesforce with other Customer data sources. | 2017-08-31
15781 | Customer Satisfaction | Minimise failed truck rolls/Telstra appointments
15781 | Cost - Avoidance | Introduce Self Install option for NBN Telstra business customers, removing the need for CT to attend the majority of new connects/transitions
15771 | Operational Improvements | Operational improvement on existing Siebel remediation tools and capabilities. Improving order and asset quality within Siebel to minimize EP and negative customer impact.
15736 | Other | Enabler
15719 | Risk & Compliance
15718 | Risk & Compliance
15717 | Risk & Compliance
15717 | Operational Improvements
15701 | Customer Satisfaction | Introduce and improve data entry quality for Customer and Contact level data
15701 | Legal/Regulatory Commitment | Enhance data validation checks
15638 | Customer Satisfaction
15638 | Efficiency
15638 | Operational Improvements
15589 | Customer Satisfaction | Less time in quarantine
15565 | Customer Satisfaction
15565 | Operational Improvements
15482 | Operational Improvements | Strategic Reporting will provide the business benefits KPI measurement for the CDP rollout.
15474 | Efficiency
15390 | Customer Satisfaction | To ensure that our customers’ ADSL service qualification and sales experience is greatly improved.
15388 | Cost - Reduction | Standardised and streamlined business process efficiency through a simplified fit-for-purpose strategic solution mix. Process simplification, removal of waste/idle time, reduced manual handoffs, decrease in swivel chairing/data duplication, and improved jeopardy management. Efficient and effective allocation of resources aligned to skills, location and availability. | 2017-05-29
15388 | Customer Satisfaction | Efficient and effective allocation of resources aligned to skills, location and availability will ensure customer services are provisioned sooner. | 2017-05-29
15383 | Efficiency
15370 | Revenue - Retained |  | 2016-12-04
15343 | Revenue - Incremental
15300 | Customer Satisfaction
15263 | Cost - Reduction
15263 | Customer Satisfaction
15233 | Business Launch Date
15233 | Compliance with 3rd party
15233 | Revenue - Incremental
15233 | Legal/Regulatory Commitment
15233 | Revenue - Retained
15215 | Risk & Compliance | Risk with incorrect customer and contact Data
15140 | Customer Satisfaction
15139 | Customer Satisfaction
15138 | Customer Satisfaction
15068 | Revenue - Incremental | The product will generate incremental revenue for Telstra | 2018-03-18
14954 | Efficiency
14954 | Legal/Regulatory Commitment
14888 | Cost - Reduction | Fulfil USO obligations in a more cost effective manner
14771 | Efficiency | To be able to use a system that is made for our current network
14771 | Existing Capability | Existing capability is lacking in TRAC for Transport Inventory.
14729 | Operational Improvements
14729 | Customer Satisfaction
14719 | Operational Improvements
14695 | Customer Satisfaction | • Inconsistent customer experience between Telstra Wholesale domestic and Telstra GES International products; • Receipt of separate bills for domestic and International products from same Telstra; and • Signing separate contracts when expanding services into Australia
14642 | Legal/Regulatory Commitment | Meeting PCI compliance is a regulatory requirement | 2017-06-30
14600 | Cost - Reduction
14600 | Efficiency
14526 | Legal/Regulatory Commitment | Requirement to comply with international accounting standard (IFRS15) by start of FY18 | 2017-06-30
14468 | Revenue - Retained | Telstra will be in a position to identify customers being over or under charged | 2017-01-31
14468 | Customer Satisfaction | Telstra will be in a position to proactively correct data issues impacting on privacy and serviceability | 2017-01-31
14436 | Revenue - Retained
14405 | Other | Marketing Campaign
14358 | Cost - Reduction | Improvement in strategic and transaction NPS
14234 | Operational Improvements
14190 | Operational Improvements
14151 | Operational Improvements
14077 | Customer Satisfaction
13998 | Compliance with 3rd party | Comply with government data retention legislation
13982 | Operational Improvements

## Dependencies
IR_Number | Dependencies.Dependency_Type | Dependencies.DependantIR.IR_Number | Dependencies.Description
17076 | IR | 16504
17048 | Functional (Applcation and Data) | 16750 | MAXIM and SDDB changes
17022 | IR | 16818 | IR16818 is preliminary to this IR. expand Express gateway verification functionality to Advanced.
17010 | Functional (Applcation and Data) |  | Deployment of 1BC Drop 1 on 8 Sept 2017. This deployment was completed.
17005 | IR | 15945
17002 | IR | 16630
16941 | IR | 16532
16898 | IR | 16586
16801 | IR | 16109 | IR16109 must deploy first to ensure 16801 can deploy
16767 | IR | 16764 | 16764 to be deployed on Nov-2017-Timeframe
16730 | IR | 15829
16730
16730 | IR | 15781
16703 | IR | 15215
16605 | Technical (Hardware or Network) | 16109 | Silent line safe select changes ca be toggled on once changes in Siebel have been implemented
16541 | Functional (Applcation and Data) | 15913 | Foxtel Now partner on boarding and billing functionalities depends on Billing Agent core functionalities being built as part of IR15913
16503 | Functional (Applcation and Data) | 16034 | IR 16034 - MICA changes to be deployed if this IR need to deployed
16484 | Other |  | Asurion has to deploy
16466 | IR | 16486 | Dependency on FTTC Deemed Order project for CURLS to add PCMS code and generate daily license files for AXIS, SIIAM and RASS-P. This functionality is required to be available in CURLS for FTTC Continuity-C Assurance solution to be able to meet its Phase 1 BRT requirements and timeframes. PCMS code to be provided in a new field and PRI number in an existing field. No changes in the file format for CMART, and CURLS to CMART frequency will continue to be weekly.
16466 | IR | 16487 | Dependency on FTTC Continuity-C Activations project to add PCMS codes for Continuity-C services in PMA in time for testing of the FTTC Continuity-C Assurance IR16466 solution as part of Phase 1 delivery. AXIS and RASS-P cannot tag the services with LSL license ID until the new PCMS code for LSL license tagging is introduced in PMA by FTTC Continuity-C Activations project.
16443 | IR | 15767 | This IR is dependent on the delivery of IR15767
16381 | Functional (Applcation and Data) | 16379 | IR16379 must be implemented before this is deployed
16381 | Functional (Applcation and Data) | 14190 | IR14190 must be implemented before this is deployed
16363 | IR | 15638
16301 | IR | 14497
16281 | Other |  | Requires the Azure platform to be ready and available to use - Cloud enablement are providing this
16265 | Functional (Applcation and Data) |  | This IR is the 2nd scope of IR14497.
16202 | Functional (Applcation and Data) | 15250
15781 | IR | 15919 | Phase 1 of Service Migragation and Self Install
15719 | IR | 15718 | iTAM UP Phase 1
15370 | IR | 14198 | This is the first Drop of the Billing solution
15233 | IR | 15445
15215 | IR | 14468 | The dependency is that we need to deploy IR14468 to enable the delivery of IR15215 functionality.
15140 | IR | 15139
15140 | IR | 15138
15140 | IR | 14989
14771 | IR | 15435
14771 | IR | 15433
14771 | IR | 15429
14695 | IR | 13279 | This IR is dependent on deployment of IR13279
14526 |  | 14097
14234 | IR | 12944
14190 | Technical (Hardware or Network) |  | There is a hard dependency for the new network element (DPI - Deep Packet Inspection) as well as the network solution to be in place in the model environment in order for integration testing (CAT) to commence.

## DeployActivities
IR_Number | Deployment_Activities.Application | Deployment_Activities.Status | Deployment_Activities.Change_Start_Date | Deployment_Activities.Change_End_Date | Deployment_Activities.Workstream | Deployment_Activities.CRQ_id | Deployment_Activities.Activity_Type | Deployment_Activities.Delivered_Businesss_Value
17226 | MICA | Target | 2017-10-27 | 2017-10-29 | Digital Markets - Digital Prod - MICA Legacy
17162 | CONNECT | Target | 2018-01-19 | 2018-01-19 | TSE - BIOS - Solution Delivery
17162 | PROMISE | Target | 2018-01-19 | 2018-01-19 | TSE - BIOS - Solution Delivery
17162 | TOOLKIT | Target | 2018-01-19 | 2018-01-19 | TSE - BIOS - Solution Delivery
17162 | WOM-AE | Target | 2018-01-19 | 2017-10-19 | TSE - BIOS - Solution Delivery
17140 | BILL-PAY | Target | 2017-10-06 | 2017-10-06 | Retail Engagement - Billing - Corporate & Payment | CRQ000003131440 | Other
17140 | DI-DIGITALSHOP | Target | 2017-10-05 | 2017-10-06 | Digital Markets | CRQ000003058529 | Other
17121 | CCB-PROD-CAT | Target | 2017-10-28 | 2017-10-28 | Digital Markets - Digital Prod - Prodcat
17121 | SDF | Target | 2017-10-28 | 2017-10-28 | TSE - Software Engineering
17121 | PRE-PAID-ACTIVATION | Target | 2017-10-28 | 2017-10-28 | TSE - Software Engineering
17121 | PREPAIDRECHARGEONLINE | Target | 2017-10-28 | 2017-10-28 | TSE - Software Engineering
17119 | MAPS4P | Target | 2017-10-27 | 2017-10-27 | TSE - BIOS - Solution Delivery
17108 | MAXIM | Target | 2017-12-02 | 2017-12-02 | TSE - Software Engineering |  | Functional
17108 | MAXIM-OBIEE | Target | 2017-12-02 | 2017-12-02 | TSE - Software Engineering
17079 | WAS | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Solution Delivery
17079 | TBB-OOT | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
17079 | DB-OOT | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
17079 | UCS | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Solution Delivery
17079 | CMP | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Billing
17079 | ONDB | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Billing
17077 | LNPCIS | Target | 2018-01-20 | 2018-01-21 | Digital Markets - Digital Prod -Digitisation Wsale |  | Functional
17076 | CCB-PROD-CAT | Target | 2017-11-18 | 2017-11-19 | Digital Markets - Digital Prod - Prodcat
17076 | RIFDI | Target | 2017-11-19 | 2017-11-19 | TSE - BIOS - Billing
17076 | CCB-RBILL | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - Billing
17062 | CCB-RCRM | Target | 2017-11-10 | 2017-11-11 | TSE - Customer Order Management & Sales | CRQ000003160048
17048 | A4B-OOT | Target | 2017-11-17 | 2017-11-17 | TSE - Software Engineering |  | Functional
17038 | CCB-EAI | Target | 2017-11-30 | 2017-11-30 | TSE - BIOS - BPM & Integration COE
17012 | ISL-FUL | Target | 2017-10-13 | 2017-10-13 | TSE - BIOS - BPM & Integration COE
17010 | WOM-AE | Target | 2017-10-20 | 2017-10-20 | TSE - BIOS - Solution Delivery
17010 | CONNECT | Target | 2017-10-20 | 2017-10-20 | TSE - BIOS - Solution Delivery
17010 | PROMISE | Target | 2017-10-20 | 2017-10-20 | TSE - BIOS - Solution Delivery
17001 | CCB-EAI | Target | 2017-11-30 | 2017-11-30 | TSE - BIOS - BPM & Integration COE
17001 | TCM | Target | 2017-11-30 | 2017-11-30 | TSE - Customer Order Management & Sales
17000 | CCB-RCRM | Target | 2017-10-28 | 2017-10-28 | TSE - Customer Order Management & Sales
17000 | SDF | Target | 2017-10-28 | 2017-10-28 | TSE - Software Engineering
16994 | TID-DAC | Target | 2017-09-23 | 2017-09-24 | TSE - BIOS - Solution Delivery | CRQ000003099951
16989 | MAXIM | Target | 2018-03-10 | 2018-01-13 | TSE - Software Engineering |  | Functional
16989 | CNS-DI | Target | 2018-03-10 | 2018-01-13 | TSE - Software Engineering |  | Functional
16982 | CALMS | Target | 2017-11-25 | 2017-11-25 | TELSTRA - NON-IT
16982 | CT-BILL | Target | 2017-11-25 | 2017-11-25 | TELSTRA - NON-IT
16982 | CDBOR | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Billing
16982 | AURORA | Target | 2017-11-25 | 2017-11-25 | ITS - Corporate
16982 | ONDB | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Billing
16982 | WAS | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Solution Delivery
16982 | CCB-RBILL | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Billing
16982 | MICA | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Billing
16982 | FLEXCAB | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Billing
16980 | ONDB | Confirmed | 2017-09-15 | 2017-09-16 | TSE - BIOS - Billing | CRQ000003098389
16973 | TDI-IDM | Target | 2017-10-05 | 2017-10-05 | TSE - Software Engineering | CRQ000003156717
16973 | CONNECT | Target | 2017-10-13 | 2017-10-13 | TSE - BIOS - Solution Delivery | CRQ000003160805
16973 | WAS | Target | 2017-12-16 | 2017-12-16 | TSE - BIOS - Solution Delivery
16973 | RAA | Target | 2017-10-18 | 2017-10-18 | TSE - Software Engineering
16973 | TBB-OOT | Target | 2017-12-16 | 2017-12-16 | TSE - Software Engineering
16973 | DB-OOT | Target | 2017-11-04 | 2017-11-04 | TSE - Software Engineering
16972 | XD | Target | 2017-10-15 | 2017-10-15 | Retail Engagement - Frontline Desktop Automation |  | Functional
16971 | TPNI | Target | 2018-02-23 | 2018-02-25 | Engagement - Digital Markets - NBN - DA |  | Functional
16965 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16963 | CCB-RCRM | Target | 2017-11-03 | 2017-11-05 | TSE - Customer Order Management & Sales
16961 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16959 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16955 | CCB-RCRM | Target | 2017-10-13 | 2017-10-15 | TSE - Customer Order Management & Sales
16953 | CCB-EAI | Target | 2018-04-08 | 2018-04-08 | TSE - BIOS - BPM & Integration COE |  | Functional
16953 | ESF-SS | Target | 2018-04-08 | 2018-04-08 | TSE - BIOS - BPM & Integration COE |  | Functional
16953 | OM-FUL | Target | 2018-04-08 | 2018-04-08 | TSE - BIOS - Solution Delivery |  | Functional
16953 | CCB-RCRM | Target | 2018-04-08 | 2018-04-08 | TSE - Customer Order Management & Sales |  | Functional
16949 | MAXIM-OBIEE | Target | 2017-11-12 | 2017-11-12 | Digital Markets - Digital Prod - NBN IT Prog Del |  | Functional
16948 | CCB-EAI | Target | 2017-09-28 | 2017-09-28 | TSE - BIOS - BPM & Integration COE | CRQ000003164116 | Functional
16946 | BILL-PAY | Target | 2017-10-19 | 2017-10-19 | Retail Engagement - Billing - Corporate & Payment |  | Functional
16946 | MYACCOUNT | Target | 2017-10-24 | 2017-10-24 | TSE - Software Engineering |  | Functional
16945 | CCB-PROD-CAT | Target | 2017-09-26 04:30 | 2017-09-26 04:30 | Digital Markets - Digital Prod - Prodcat
16944 | B2BGW-VIVA | Target | 2017-10-06 | 2017-10-06 | TSE - BIOS - BPM & Integration COE | CRQ000003158400
16939 | SDF | Target | 2017-11-27 | 2017-11-27 | TSE - Software Engineering
16939 | RAA | Target | 2017-11-19 | 2017-11-19 | TSE - Software Engineering
16939 | TDI-EM | Target | 2017-11-19 | 2017-11-19 | TSE - Software Engineering
16936 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16935 | ONLINESHOP | Target | 2017-11-05 | 2017-11-06 | TSE - Software Engineering
16933 | INTEGRALPLUS | Target | 2017-10-21 | 2017-10-27 | TSE - BIOS - Solution Delivery | CRQ000003182246 | Functional
16933 | EPM | Target | 2017-10-27 | 2017-10-27 | ITS - Corporate | CRQ000003182246 | Test Support
16933 | EMSBB | Target | 2017-10-27 | 2017-10-27 | TSE - BIOS - BPM & Integration COE | CRQ000003182246 | Test Support
16933 | SEGWAY | Target | 2017-10-27 | 2017-10-27 | TSE - BIOS - BPM & Integration COE | CRQ000003182246 | Test Support
16926 | CCB-PROD-CAT | Target | 2017-12-08 05:30 | 2017-12-08 05:30 | Digital Markets - Digital Prod - Prodcat
16923 | ISL-FUL | Confirmed | 2017-08-25 | 2017-08-25 | TSE - BIOS - BPM & Integration COE | CRQ000003052984
16923 | T&DM | Target | 2017-09-08 | 2017-09-08 | TSE - BIOS - Solution Delivery
16923 | IVR-ERAD | Target | 2017-09-06 | 2017-09-08 | TSE - Customer Contact Capabilities
16923 | SENTINEL | Target | 2017-08-29 | 2017-08-29 | TSE - Software Engineering
16923 | EDW | Confirmed | 2017-08-25 | 2017-08-27 | TSE - BI Delivery | CRQ000003099513
16915 | CRAMER-LI | Target | 2018-02-28 | 2018-02-28 | TSE - BIOS - Solution Delivery
16915 | NDSD | Target | 2019-02-28 | 2018-02-28 | TSE - BIOS - Solution Delivery
16911 | NTT | Target | 2018-03-03 | 2018-03-03 | Engagement - Digital Markets - NBN - DA
16910 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16902 | BILL-PAY | Target | 2018-05-31 | 2018-05-31 | Retail Engagement - Billing - Corporate & Payment |  | Functional
16901 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16900 | IPDAM | Target | 2018-02-02 | 2018-02-03 | TSE - BIOS - Solution Delivery
16900 | NSA-CACHE | Target | 2018-02-02 | 2018-02-03 | TSE - BIOS - Solution Delivery
16900 | CRAMER-LI | Target | 2018-02-02 | 2018-02-03 | TSE - BIOS - Solution Delivery
16900 | IP-RDM | Target | 2018-02-02 | 2018-02-03 | TSE - BIOS - Solution Delivery
16900 | NPMAN | Target | 2018-02-02 | 2018-02-03 | TSE - BIOS - Solution Delivery
16897 | UNI-COM | Target | 2017-09-16 | 2017-09-17 | TSE - BIOS - Solution Delivery |  | Functional
16892 | CCB-RCRM | Target | 2017-11-18 | 2017-11-18 | TSE - Customer Order Management & Sales
16892 | RCONOE | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - Billing
16885 | BILL-PAY | Target | 2017-11-26 | 2017-11-26 | Retail Engagement - Billing - Corporate & Payment |  | Functional
16882 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16869 | CCB-RCRM | Target | 2017-10-14 | 2017-10-15 | TSE - Customer Order Management & Sales | CRQ000003156972
16862 | CCB-RCRM | Target | 2018-02-18 | 2018-02-18 | TSE - Customer Order Management & Sales
16851 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16836 | BAMBI | Confirmed | 2017-09-28 | 2017-09-29 | TSE - BIOS - Operational Data & Analytics | CRQ000003135544 | Functional
16836 | CONNECT | Target | 2017-09-29 | 2017-09-30 | TSE - BIOS - Solution Delivery |  | Reference Data
16836 | ESF-SS | Confirmed | 2017-09-29 | 2017-09-30 | TSE - BIOS - BPM & Integration COE | CRQ000003139264 | Functional
16836 | E-BPM-NBN-BUSINESS | Target | 2017-09-29 | 2017-09-30 | TSE - BIOS - BPM & Integration COE | CRQ000003096330 | Functional
16818 | CCB-RCRM | Target | 2017-11-18 | 2017-11-18 | TSE - Customer Order Management & Sales
16816 | CCB-RCRM | Target | 2017-10-26 | 2017-10-26 | TSE - Customer Order Management & Sales
16816 | BSL | Target | 2017-10-26 | 2017-10-26 | TSE - BIOS - Operational Data & Analytics
16809 | SOM-B2B | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering |  | Functional
16809 | CNS-DI | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering |  | Functional
16809 | IPD-RPA | Target | 2017-11-11 | 2017-11-12 | TELSTRA - NON-IT
16796 | OM-FUL | Target | 2017-10-06 | 2017-10-06 | TSE - BIOS - Solution Delivery
16792 | MAXIM | Target | 2018-01-13 | 2018-01-14 | TSE - Software Engineering |  | Functional
16790 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16782 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16780 | TID-EAI | Target | 2018-02-09 | 2018-02-09 | TSE - BIOS - BPM & Integration COE
16778 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16767 | CURLS | Target | 2018-02-16 | 2018-02-18 | Engagement - Digital Markets - NBN - DA
16767 | NDSD | Target | 2018-02-16 | 2018-02-18 | Engagement - Digital Markets - NBN - DA
16766 | ISL-FUL | Withdrawn | 2017-08-25 | 2017-08-25 | TSE - BIOS - BPM & Integration COE
16766 | T&DM | Withdrawn | 2017-08-25 | 2017-08-25 | TSE - BIOS - Solution Delivery
16765 | OM-FUL | Confirmed | 2017-08-25 | 2017-08-25 | TSE - BIOS - Solution Delivery | CRQ000002727044
16764 | NPAMS | Target | 2017-11-25 | 2017-11-25 | TSE - BIOS - Solution Delivery
16764 | NTT | Target | 2017-11-24 | 2017-11-26 | Engagement - Digital Markets - NBN - DA
16764 | SFX | Target | 2017-11-24 | 2017-11-26 | TSE - BIOS - BPM & Integration COE
16764 | CURLS | Target | 2017-11-24 | 2017-11-26 | Engagement - Digital Markets - NBN - DA
16764 | NDSD | Target | 2017-11-24 | 2017-11-26 | Engagement - Digital Markets - NBN - DA
16759 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16758 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16757 | CCB-PROD-CAT | Target | 2017-10-06 05:30 | 2017-10-06 05:30 | Digital Markets - Digital Prod - Prodcat
16750 | MAXIM | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
16750 | SDDB | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
16730 | E-BPM-NBN-BUSINESS | Target | 2017-11-17 | 2017-11-18 | TSE - BIOS - BPM & Integration COE |  | Functional Other
16727 | CMP | Confirmed | 2017-09-30 | 2017-09-30 | TSE - BIOS - Billing | CRQ000003132988
16727 | CBIS | Confirmed | 2017-09-30 | 2017-09-30 | TSE - BIOS - Billing | CRQ000003134170
16709 | CCB-RCRM | Target | 2017-12-15 | 2017-09-15 | TSE - Customer Order Management & Sales
16709 | CTI-AWBT | Target | 2017-12-15 | 2017-12-15 | TSE - Customer Contact Capabilities
16709 | CCB-RM-RA | Target | 2017-12-15 | 2017-12-15 | Media and Marketing
16709 | T-DDC | Target | 2017-12-15 | 2017-12-15 | TSE - Software Engineering
16709 | EDW | Target | 2017-12-15 | 2017-12-15 | TSE - BI Delivery
16709 | ATHENIAN | Target | 2017-12-15 | 2017-12-15 | Finance & Strategy - C&P
16709 | SENTINEL | Target | 2017-12-15 | 2017-12-15 | TSE - Software Engineering
16709 | CCB-RBILL | Target | 2017-12-15 | 2017-12-15 | TSE - BIOS - Billing
16709 | UNI-COM | Target | 2017-12-15 | 2017-12-15 | TSE - BIOS - Solution Delivery
16704 | NBNPLUS-MICROSERVICES | Target | 2017-11-13 | 2017-11-13 | TSE - Software Engineering
16704 | SDF | Target | 2017-11-13 | 2017-11-13 | TSE - Software Engineering
16697 | CURLS | Target | 2018-02-23 | 2018-02-25 | Engagement - Digital Markets - NBN - DA |  | Functional
16697 | AXIS | Target | 2018-02-23 | 2018-02-25 | TSE - BIOS - Solution Delivery |  | Functional
16697 | NTT | Target | 2018-02-23 | 2018-02-25 | Engagement - Digital Markets - NBN - DA |  | Functional
16693 | BILL-PAY | Target | 2017-09-12 | 2017-09-12 | Retail Engagement - Billing - Corporate & Payment |  | Other
16693 | BILL-PAY | Target | 2017-09-24 | 2017-09-24 | Retail Engagement - Billing - Corporate & Payment |  | Other
16693 | BILL-PAY | Confirmed | 2017-08-08 | 2017-08-08 | Retail Engagement - Billing - Corporate & Payment | CRQ000003018719 | Other
16684 | OM-FUL | Target | 2017-10-06 | 2017-10-06 | TSE - BIOS - Solution Delivery | CRQ000002747199 | Functional
16677 | OM-FUL | Target | 2017-10-06 | 2017-10-07 | TSE - BIOS - Solution Delivery
16666 | OM-FUL | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Solution Delivery |  | Functional
16666 | MAXIM | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering |  | Functional
16666 | UNI-COM | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - Solution Delivery |  | Functional
16665 | CURLS | Target | 2017-10-27 | 2017-10-30 | Engagement - Digital Markets - NBN - DA |  | Functional Test Support
16653 | EMSBB | Confirmed | 2017-09-08 | 2017-09-08 | TSE - BIOS - BPM & Integration COE | CRQ000003118583
16649 | SIIAM | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - Solution Delivery
16649 | LOLS | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - Solution Delivery
16649 | SHARP-EDGE | Target | 2018-01-13 | 2018-01-13 | Finance & Strategy - C&P
16649 | PROMISE | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - Solution Delivery
16649 | WOM-AE | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - Solution Delivery
16649 | SFX | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - BPM & Integration COE
16649 | TOOLKIT | Target | 2018-01-13 | 2018-01-13 | TSE - BIOS - Solution Delivery
16640 | MAXIM | Target | 2017-11-04 | 2017-11-05 | TSE - Software Engineering
16640 | SFX | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - BPM & Integration COE
16640 | SFDC | Target | 2017-11-04 | 2017-11-05 | TSE - Customer Order Management & Sales
16630 | FPD | Target | 2018-02-24 | 2018-02-25 | Retail Engagement - Credit & Fraud |  | Functional
16622 | NTT | Target | 2017-11-18 | 2017-11-18 | Engagement - Digital Markets - NBN - DA
16615 | CPM | Target | 2017-10-27 | 2017-10-30 | ITS - Corporate
16612 | CCB-RCRM | Target | 2017-09-30 | 2017-09-30 | TSE - Customer Order Management & Sales | CRQ000003004277
16609 | CCB-PROD-CAT | Target | 2017-10-07 05:30 | 2017-10-07 05:30 | Digital Markets - Digital Prod - Prodcat
16605 | MYACCOUNT | Target | 2017-11-24 | 2017-11-24 | TSE - Software Engineering
16605 | SDF | Target | 2017-11-24 | 2017-11-24 | TSE - Software Engineering
16598 | SDF | Target | 2017-10-14 | 2017-10-15 | TSE - Software Engineering
16595 | MOVE-ROBOT | Target | 2017-09-04 | 2017-09-04 | Retail Engagement - Frontline Desktop Automation |  | Functional
16578 | CONNECT | Target | 2017-09-29 | 2017-09-29 | TSE - BIOS - Solution Delivery
16578 | TOOLKIT | Target | 2017-09-29 | 2017-09-30 | TSE - BIOS - Solution Delivery
16578 | WFM-WOM | Target | 2017-09-29 | 2017-09-30 | TSE - BIOS - Solution Delivery
16578 | PROMISE | Target | 2017-09-29 | 2017-09-30 | TSE - BIOS - Solution Delivery
16574 | CNS-DI | Target | 2017-10-14 | 2017-10-15 | TSE - Software Engineering | CRQ000003133607 | Functional
16574 | ISL-FUL | Target | 2017-10-14 | 2017-10-15 | TSE - BIOS - BPM & Integration COE |  | Reference Data
16574 | LOLO-NBN | Target | 2017-10-14 | 2017-10-15 | Digital Markets - Digital Prod -Digitisation Wsale | CRQ000003180012 | Functional
16561 | CCB-RCRM | Target | 2017-11-12 | 2017-11-12 | TSE - Customer Order Management & Sales
16553 | MAXIM | Confirmed | 2017-09-09 | 2017-09-09 | TSE - Software Engineering | CRQ000003080059
16553 | CNS-DI | Confirmed | 2017-09-09 | 2017-09-09 | TSE - Software Engineering | CRQ000003099995
16552 | CCB-RCRM | Target | 2018-02-18 | 2018-02-18 | TSE - Customer Order Management & Sales
16552 | CCB-RPRM | Target | 2018-02-18 | 2018-02-18 | TSE - Customer Order Management & Sales
16549 | FLEXCAB | Target | 2017-09-22 | 2017-09-25 | TSE - BIOS - Billing | CRQ000003076573
16541 | CCB-RBILL | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - Billing
16506 | CCB-PROD-CAT | Target | 2017-10-30 05:30 | 2017-10-30 05:30 | Digital Markets - Digital Prod - Prodcat
16504 | CDRLIVE | Target | 2017-11-05 | 2017-11-05 | Finance & Strategy - C&P
16504 | RIFDI | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | ONLINESHOP | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering
16504 | CCB-PROD-CAT | Target | 2017-11-05 | 2017-11-05 | TSE - Customer Order Management & Sales
16504 | CCB-RBILL | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | CCB-RCRM | Target | 2017-11-05 | 2017-11-05 | TSE - Customer Order Management & Sales
16504 | RCONOE | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | CCB-EAI | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE
16504 | SDF | Target | 2017-11-05 | 2017-11-05 | TSE - Software Engineering
16504 | CCB-OLB | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | DM-RBMS | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | TACBAS | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - Billing
16504 | ANDROID-24X7 | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering
16504 | MYACCOUNT | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering
16503 | CCB-COMM | Target | 2017-09-29 | 2017-09-29 | Retail Engagement - Frontline Customer Channels | CRQ000003115853
16497 | T-DDC | Target | 2017-12-21 | 2017-12-21 | TSE - Software Engineering
16497 | TDI-IDM | Target | 2017-12-04 | 2017-12-04 | TSE - Software Engineering
16487 | CURLS | Target | 2018-02-16 | 2018-02-19 | Engagement - Digital Markets - NBN - DA |  | Functional Reference Data Test Support
16487 | EMSBB | Target | 2018-02-16 | 2018-02-19 | TSE - BIOS - BPM & Integration COE |  | Functional Test Support
16487 | MQ-HUB | Target | 2018-02-16 | 2018-02-19 | TSE - BIOS - BPM & Integration COE |  | Functional Test Support
16487 | ESF-BC | Target | 2018-02-16 | 2018-02-19 | TSE - BIOS - BPM & Integration COE |  | Functional Test Support
16487 | NDSD | Target | 2018-02-16 | 2018-02-19 | Engagement - Digital Markets - NBN - DA |  | Functional Test Support
16487 | PLR | Target | 2018-02-16 | 2018-02-19 | Finance & Strategy BU - GFS |  | Functional Test Support
16487 | NPAMS | Target | 2018-02-16 | 2018-02-19 | TSE - BIOS - Solution Delivery |  | Test Support Functional
16487 | AXIS | Target | 2018-02-16 | 2018-02-19 | TSE - BIOS - Solution Delivery |  | Functional Test Support
16486 | CURLS | Target | 2017-10-27 | 2017-10-29 | Engagement - Digital Markets - NBN - DA | CRQ000003167838 | Functional
16486 | NTT | Target | 2017-10-20 | 2017-10-21 | Engagement - Digital Markets - NBN - DA | CRQ000003178182 | Other
16486 | NDSD | Target | 2017-10-27 | 2017-10-29 | Engagement - Digital Markets - NBN - DA | CRQ000003143651 | Functional
16486 | SFX | Target | 2017-10-27 | 2017-10-29 | Engagement - Digital Markets - NBN - DA | CRQ000003185606 | Other
16484 | YTT | Target | 2017-10-14 | 2017-10-14 | TSE - Software Engineering |  | Functional
16484 | RAA | Target | 2017-10-14 | 2017-10-14 | TSE - Software Engineering
16467 | DSAPI | Target | 2017-10-03 | 2017-10-03 | TSE - Software Engineering
16466 | TOOLKIT | Target | 2017-09-30 | 2017-10-01 | TSE - BIOS - Solution Delivery | CRQ000003101688
16466 | RASS-P | Target | 2017-10-13 | 2017-10-14 | TSE - Software Engineering | CRQ000003127900
16466 | TOOLKIT | Target | 2017-10-14 | 2017-10-14 | TSE - BIOS - Solution Delivery | CRQ000003101685
16466 | AXIS | Target | 2017-10-13 | 2017-10-14 | TSE - BIOS - Solution Delivery | CRQ000003127901
16465 | CONNECT | Target | 2017-09-22 | 2017-09-23 | TSE - BIOS - Solution Delivery
16450 | CNS-DI | Target | 2017-11-04 | 2017-11-05 | TSE - Software Engineering |  | Functional
16447 | B2BGW-VIVA | Target | 2017-10-28 | 2017-10-29 | TSE - BIOS - BPM & Integration COE
16443 | EDW | Target | 2017-10-21 | 2017-10-21 | TSE - BI Delivery
16443 | CDE | Target | 2017-10-21 | 2017-10-22 | Retail Engagement - Credit & Fraud |  | Functional
16443 | CCB-RBILL | Target | 2017-10-21 | 2017-10-22 | TSE - BIOS - Billing |  | Functional
16436 | CCB-RBILL | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Billing |  | Test Support
16436 | CCB-RPRM | Target | 2017-11-04 | 2017-11-05 | TSE - Customer Order Management & Sales |  | Functional
16436 | ONESOURCE | Target | 2017-11-04 | 2017-11-05 | TSE - Software Engineering |  | Test Support
16436 | AM-SHARED1 | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Solution Delivery |  | Test Support
16436 | ISL-FUL | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Test Support
16436 | CRAMER-LI | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Solution Delivery |  | Test Support
16436 | CONNECT | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Solution Delivery |  | Test Support
16436 | CCB-PROD-CAT | Target | 2017-11-04 | 2017-11-05 | Digital Markets - Digital Prod - Prodcat |  | Functional
16436 | B2BGW-VIVA | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Test Support
16436 | AXIS | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Solution Delivery |  | Test Support
16436 | SDF | Target | 2017-11-04 | 2017-11-05 | TSE - Software Engineering |  | Test Support
16436 | CUSTOMER-ADVISORY-TOOL | Target | 2017-11-04 | 2017-11-05 | TSE - Software Engineering |  | Test Support
16436 | CCB-RCRM | Target | 2017-11-04 | 2017-11-05 | TSE - Customer Order Management & Sales |  | Functional
16436 | CCB-EAI | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Test Support
16433 | TPNI | Target | 2017-10-20 | 2017-10-22 | Engagement - Digital Markets - NBN - DA | CRQ000003146656 | Functional
16433 | NDSD | Target | 2017-10-20 | 2017-10-22 | Engagement - Digital Markets - NBN - DA | CRQ000003143664 | Functional
16431 | DIAGNOSTICS | Deployed | 2017-08-31 | 2017-08-31 | TSE - BIOS - Solution Delivery | CRQ000003112179 | Functional
16431 | SIIAM | Confirmed | 2017-09-28 | 2017-09-28 | TSE - BIOS - Solution Delivery | CRQ000003114267 | Functional
16431 | T&DM | Target | 2017-10-06 | 2017-10-06 | TSE - BIOS - Solution Delivery | CRQ000003157826 | Functional
16431 | TOPS | Confirmed | 2017-09-28 | 2017-09-28 | TSE - Software Engineering | CRQ000003131002 | Functional
16431 | OKAPI-SAAS | Target | 2017-09-28 | 2017-09-28 | Cloud Engineering - Core Engineering | CRQ000003155890 Wholesale-Trouble-Ticket CRQ000003155889 Wholesale-Demo-Trouble-Ticket CRQ000003155896 Wholesale-Pull-Notification CRQ000003155897 Wholesale-Demo-Pull-Notification | Functional
16430 | DQA | Target | 2018-03-30 | 2018-03-30 | TSE - BIOS - Data Alignment
16416 | OKAPI | Withdrawn | 2017-10-26 | 2017-10-27 | Cloud Engineering - Multi Cloud
16416 | IVR-CEM | Target | 2017-12-01 | 2017-12-01 | TSE - Customer Contact Capabilities
16416 | CARES | Target | 2017-12-01 | 2017-12-01 | TSE - BIOS - Solution Delivery
16400 | CCB-RCRM | Target | 2017-06-13 | 2017-11-05 | TSE - Customer Order Management & Sales
16390 | CCB-RCRM | Target | 2017-10-14 | 2017-10-15 | TSE - Customer Order Management & Sales
16390 | CCB-RBILL | Target | 2017-10-14 | 2017-10-15 | TSE - BIOS - Billing
16390 | RAPTOR-E | Target | 2017-10-02 | 2017-10-02 | Finance & Strategy - C&P
16390 | TCM | Target | 2017-10-02 | 2017-10-02 | TSE - Customer Order Management & Sales
16390 | CDRLIVE | Target | 2017-10-02 | 2017-10-02 | Finance & Strategy - C&P
16390 | CCB-PROD-CAT | Target | 2017-10-14 | 2017-10-15 | Digital Markets - Digital Prod - Prodcat
16390 | EDW | Target | 2017-10-02 | 2017-10-02 | TSE - BI Delivery
16360 | ONDB | Target | 2018-04-28 | 2018-04-29 | TSE - BIOS - Billing | CRQ123456123456 | Functional
16342 | ISDW | Target | 2017-10-27 | 2017-10-28 | Finance & Strategy - C&P
16342 | CONNECT | Target | 2017-10-27 | 2017-10-28 | TSE - BIOS - Solution Delivery
16342 | CRUX | Target | 2017-10-27 | 2017-10-28 | TSE - BIOS - Solution Delivery
16342 | TOOLKIT | Withdrawn | 2017-10-27 | 2017-10-28 | TSE - BIOS - Solution Delivery
16342 | TRUECOMP | Withdrawn | 2017-10-27 | 2017-10-28 | TSE - BIOS - Solution Delivery
16342 | PLR | Target | 2017-10-27 | 2017-10-28 | TELSTRA - NON-IT
16342 | SFX | Target | 2017-10-27 | 2017-10-28 | TSE - BIOS - BPM & Integration COE
16322 | R&E | Target | 2017-11-10 | 2017-11-10 | TSE - Software Engineering
16322 | TDI-IDM | Target | 2017-11-10 | 2017-11-10 | TSE - Software Engineering
16311 | MNC | Target | 2018-02-17 | 2018-02-18 | TSE - Customer Order Management & Sales
16311 | MICA | Withdrawn | 2017-11-11 | 2017-11-11 | TSE - BIOS - Billing
16311 | FLEXCAB | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Billing
16311 | SFX | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
16311 | UOMS | Target | 2018-02-17 | 2018-02-18 | Retail Engagement - Billing - Corporate & Payment
16305 | B2BGW-VIVA | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - BPM & Integration COE | CRQ000003091740
16305 | EMSBB | Target | 2017-09-08 | 2017-09-09 | TSE - BIOS - BPM & Integration COE | CRQ000003093816
16305 | ESF-BC | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - BPM & Integration COE | CRQ000003102867
16301 | TW-QUOTE2ORDER | Target | 2017-10-27 | 2017-10-28 | TSE - Software Engineering |  | Functional
16301 | SQ-CENTRAL | Target | 2017-10-27 | 2017-10-28 | TSE - Software Engineering |  | Functional
16289 | SIIAM | Target | 2017-09-21 | 2017-09-21 | TSE - BIOS - Solution Delivery
16265 | LOLO-NBN | Target | 2017-11-04 | 2017-11-05 | Digital Markets - Digital Prod -Digitisation Wsale |  | Functional
16243 | SDF | Target | 2017-04-03 | 2017-12-15 | TSE - Software Engineering |  | Functional Other Reference Data
16243 | TDI-EM | Target | 2017-04-03 | 2017-12-15 | TSE - Software Engineering |  | Functional Other Reference Data
16240 | TCM | Target | 2018-03-03 | 2018-03-03 | TSE - Customer Order Management & Sales
16240 | TCM-EAI | Target | 2018-03-03 | 2018-03-03 | TSE - BIOS - BPM & Integration COE
16232 | IPDAM | Target | 2018-02-09 | 2018-02-10 | TSE - BIOS - Solution Delivery
16232 | CRAMER-LI | Target | 2018-02-09 | 2018-02-10 | TSE - BIOS - Solution Delivery
16232 | RDNBOSS | Target | 2018-02-09 | 2018-02-10 | TSE - BIOS - Solution Delivery
16232 | NPMAN | Target | 2018-02-09 | 2018-02-10 | TSE - BIOS - Solution Delivery
16232 | MITS | Target | 2018-02-09 | 2018-02-10 | TSE - BIOS - Solution Delivery
16232 | MAGPIE | Target | 2018-02-09 | 2018-02-10 | GB2B IT - Enterprise Consulting and Delivery
16230 | CUSTOMER-ADVISORY-TOOL | Target | 2017-11-25 | 2017-11-25 | TSE - Software Engineering
16230 | RAA | Target | 2017-11-25 | 2017-11-25 | TSE - Software Engineering
16230 | ATHENIAN | Target | 2017-11-25 | 2017-11-25 | Finance & Strategy - C&P
16207 | ITAM | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - Solution Delivery
16207 | EOMSYS | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - Solution Delivery
16207 | ESF-BC | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - BPM & Integration COE
16207 | NBNPLUS-MICROSERVICES | Target | 2017-09-09 | 2017-09-09 | TSE - Software Engineering
16207 | TCS-AUTOMATION | Target | 2017-09-09 | 2017-09-09 | TSE - Software Engineering
16207 | EMSBB | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - BPM & Integration COE
16193 | LOLO | Target | 2017-12-02 | 2017-12-02 | TSE - Software Engineering
16185 | NTT | Target | 2018-03-03 | 2018-03-03 | Engagement - Digital Markets - NBN - DA
16131 | OKAPI-SSO | Target | 2017-12-22 | 2017-12-22 | TSE - Software Engineering
16130 | SDF-M-ACG | Target | 2017-12-22 | 2017-12-22 | TSE - Software Engineering
16130 | RAA | Target | 2017-12-22 | 2017-12-22 | TSE - Software Engineering
16119 | PROMISE | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - Solution Delivery
16119 | OM-FUL | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - Solution Delivery
16119 | ISL-FUL | Target | 2017-11-18 | 2017-11-19 | TSE - BIOS - BPM & Integration COE
16119 | LOLO | Target | 2017-11-18 | 2017-11-19 | TSE - Software Engineering
16119 | CCB-RCRM | Target | 2017-11-18 | 2017-11-19 | TSE - Customer Order Management & Sales
16109 | MYACCOUNT | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
16109 | IPHONE-24X7 | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
16109 | ANDROID-24X7 | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
16109 | DI-DIGITALSHOP | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
16109 | CCB-RCRM | Target | 2018-02-18 | 2018-02-18 | TSE - Customer Order Management & Sales
16107 | NETMAPS | Target | 2017-11-25 | 2017-11-26 | TSE - BIOS - Solution Delivery |  | Functional
16101 | CCB-RBILL | Target | 2017-02-06 | 2017-11-05 | TSE - BIOS - Billing
16101 | CCB-RCRM | Target | 2017-02-06 | 2017-11-05 | TSE - Customer Order Management & Sales
16078 | OKAPI | Target | 2017-11-04 | 2017-11-15 | Cloud Engineering - Multi Cloud
16078 | SFDC | Target | 2017-11-04 | 2017-11-15 | TELSTRA - NON-IT
16078 | CUSTOMER-ADVISORY-TOOL | Target | 2017-11-04 | 2017-11-15 | TSE - Software Engineering
16078 | RNMSERVICES | Target | 2017-11-04 | 2017-11-15 | TSE - Software Engineering
16078 | RAA | Target | 2017-11-04 | 2017-11-15 | TSE - Software Engineering
16077 | BSL | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Operational Data & Analytics
16077 | BAMBI | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - BPM & Integration COE
16077 | CRAMER-LI | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Solution Delivery
16077 | LOLO | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering
16077 | CCB-RCRM | Target | 2017-11-11 | 2017-11-12 | TSE - Customer Order Management & Sales
16077 | CCB-EAI | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - BPM & Integration COE
16077 | MAXIM | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering
16077 | OMOT | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Solution Delivery
16077 | OM-FUL | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Solution Delivery
16069 | WAS | Target | 2017-09-30 | 2017-09-30 | TSE - BIOS - Solution Delivery
16069 | LAE-COMM | Target | 2017-10-20 | 2017-10-21 | Retail Engagement - Frontline Customer Channels |  | Functional
16069 | CCB-COMM | Target | 2017-10-20 | 2017-10-21 | Retail Engagement - Frontline Customer Channels |  | Functional Reference Data Infrastructure
16069 | SHARP-EDGE | Target | 2017-09-30 | 2017-09-30 | Finance & Strategy - C&P
16069 | ECHIDNA | Target | 2017-10-20 | 2017-10-21 | TSE - Customer Order Management & Sales |  | Functional
16046 | PVCS-FORMS | Target | 2017-10-13 | 2017-10-13 | TSE - Software Engineering |  | Functional
16039 | MQ-HUB | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BIOS - BPM & Integration COE | CRQ000003098905 | Functional | Yes
16039 | AVS | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BIOS - Solution Delivery | CRQ000003100279 | Other
16039 | FLEXCAB | Target | 2017-10-07 | 2017-10-07 | TSE - BIOS - Billing |  | Test Support
16039 | MICA | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BIOS - Billing | CRQ000003106675 | Other
16039 | PLR | Confirmed | 2017-10-07 | 2017-10-07 | TELSTRA - NON-IT | CRQ000003108454 | Other
16039 | AM-MOBILE | Target | 2017-10-07 | 2017-10-09 | TSE - BIOS - Solution Delivery |  | Test Support
16039 | CCB-EAI | Target | 2017-10-07 | 2017-10-09 | TSE - BIOS - BPM & Integration COE |  | Test Support
16039 | CCB-RCRM | Target | 2017-10-07 | 2017-10-09 | TSE - Customer Order Management & Sales |  | Test Support
16039 | OM-FUL | Target | 2017-10-07 | 2017-10-09 | TSE - BIOS - Solution Delivery |  | Test Support
16039 | SFX | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BIOS - BPM & Integration COE | CRQ000003095490 | Functional
16039 | MNC | Target | 2017-10-07 | 2017-10-07 | TSE - Customer Order Management & Sales |  | Test Support Other
16039 | MNPFOH | Target | 2017-10-07 | 2017-10-09 | TSE - Customer Order Management & Sales |  | Test Support
16039 | LOLM | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering |  | Test Support Other
16039 | EIN-4 | Target | 2017-10-07 | 2017-10-07 | CPE - Voice and Video - IMS Technology |  | Test Support
16039 | MNPCIS | Confirmed | 2017-10-07 | 2017-10-07 | Digital Markets - Digital Prod -Digitisation Wsale | CRQ000003094576 | Functional Infrastructure
16039 | SENTINEL | Confirmed | 2017-10-07 | 2017-10-07 | TSE - Software Engineering | CRQ000003159253 | Other
16039 | WDR | Target | 2017-10-07 | 2017-10-09 | TSE - Software Engineering | CRQ000003107416 | Other
16039 | EDW | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BI Delivery | CRQ000003107883 | Other
16039 | MEDIATOR | Target | 2017-10-07 | 2017-10-07 | TSE - BIOS - Solution Delivery | CRQ1450515 | Other
16039 | ISL-FUL | Confirmed | 2017-10-07 | 2017-10-07 | TSE - BIOS - BPM & Integration COE | CRQ000003100277 | Other
16005 | IP-RDM | Target | 2017-09-29 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000003013455
16005 | IPDAM | Target | 2017-10-20 | 2017-10-20 | TSE - BIOS - Solution Delivery | CRQ000002949383
16005 | CRAMER-LI | Target | 2017-08-26 | 2017-08-26 | TSE - BIOS - Solution Delivery
16005 | RDNBOSS | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000003011111
16005 | NPMAN | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000002937508
16005 | NDSD | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000002943015
15945 | SDF | Target | 2017-08-13 | 2017-11-03 | TSE - Software Engineering
15945 | CCB-RCRM | Target | 2017-09-24 | 2017-11-03 | TSE - Customer Order Management & Sales
15945 | CCB-PROD-CAT | Target | 2017-09-24 | 2017-11-03 | TSE - Customer Order Management & Sales
15945 | UNI-COM | Target | 2017-09-03 | 2017-11-03 | TSE - BIOS - Solution Delivery
15945 | PRE-PAID-ACTIVATION | Target | 2017-08-27 | 2017-11-03 | Digital Markets - Digital Products
15944 | IP-RDM | Target | 2017-11-30 | 2017-12-01 | TSE - BIOS - Solution Delivery
15937 | RAA | Withdrawn | 2017-11-03 | 2017-11-03 | TSE - Software Engineering
15923 | CCB-RCRM | Target | 2017-08-28 | 2018-02-17 | TSE - Customer Order Management & Sales |  | Reference Data Test Support | Yes
15923 | CCB-PROD-CAT | Target | 2017-08-28 | 2018-02-17 | Digital Markets - Digital Prod - Prodcat |  | Reference Data Test Support
15923 | CCB-RBILL | Target | 2017-08-28 | 2018-02-17 | TSE - BIOS - Billing |  | Test Support
15923 | SDF | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Reference Data Test Support
15923 | MICA | Target | 2017-08-28 | 2018-02-17 | TSE - BIOS - Billing |  | Reference Data Test Support
15923 | CUSTOMER-ADVISORY-TOOL | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Reference Data Test Support
15923 | TCOE | Target | 2017-08-28 | 2018-02-17 | TSE - Release Management COE |  | Test Support
15923 | MNC | Target | 2017-08-28 | 2018-02-17 | TSE - Customer Order Management & Sales |  | Reference Data Test Support
15923 | CDRLIVE | Target | 2017-08-28 | 2018-02-17 | Finance & Strategy - C&P |  | Reference Data Test Support
15923 | CCB-RIFDI | Target | 2017-08-28 | 2018-02-17 | TSE - BIOS - Billing |  | Test Support
15923 | PMR | Target | 2017-08-28 | 2018-02-17 | Digital Markets - Digital Prod - PMR |  | Reference Data Test Support
15923 | HARNETT | Target | 2017-08-28 | 2018-02-17 | TELSTRA - NON-IT |  | Reference Data Test Support
15923 | PMA | Target | 2017-08-28 | 2018-02-17 | Digital Markets - Digital Prod - Flexcab Legacy |  | Reference Data Test Support
15923 | EDW | Target | 2017-08-28 | 2018-02-17 | TSE - BI Delivery |  | Reference Data Test Support
15923 | YTT | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Reference Data Test Support
15923 | UOMS | Target | 2017-08-28 | 2018-02-17 | Retail Engagement - Billing - Corporate & Payment |  | Reference Data Test Support
15923 | OCM | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Reference Data Test Support
15923 | MYACCOUNT | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Test Support
15923 | FLEXCAB | Target | 2017-08-28 | 2018-02-17 | TSE - BIOS - Billing |  | Test Support
15923 | CCB-EAI | Target | 2017-08-28 | 2018-02-17 | TSE - BIOS - BPM & Integration COE |  | Test Support
15923 | ONLINESHOP | Target | 2017-08-28 | 2018-02-17 | TSE - Software Engineering |  | Reference Data
15915 | CUSTOMER-ADVISORY-TOOL | Target | 2017-10-11 | 2017-10-11 | TSE - Software Engineering | CRQ123456123456 | Functional
15915 | OKAPI | Withdrawn | 2017-09-13 | 2017-09-13 | Cloud Engineering - Multi Cloud
15913 | EMSBB | Confirmed | 2017-09-29 | 2017-09-29 | TSE - BIOS - BPM & Integration COE | CRQ000003141180
15913 | CCB-EAI | Target | 2017-09-29 | 2017-09-29 | TSE - BIOS - BPM & Integration COE | CRQ000003171492
15882 | SFDC | Target | 2017-10-07 | 2017-10-07 | TSE - Customer Order Management & Sales
15882 | MYACCOUNT | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
15882 | CUSTOMER-ADVISORY-TOOL | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
15882 | ANDROID-24X7 | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
15882 | IPHONE-24X7 | Target | 2017-10-07 | 2017-10-07 | TSE - Software Engineering
15868 | MICA | Target | 2017-10-03 | 2017-10-03 | TSE - BIOS - Billing |  | Test Support
15843 | CMP | Target | 2017-11-20 | 2017-11-20 | TSE - BIOS - Billing
15843 | CBIS | Target | 2017-11-20 | 2017-11-20 | TSE - BIOS - Solution Delivery
15829 | CCB-EAI | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15829 | UNI-COM | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - Solution Delivery
15829 | BRIGHTSTAR | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15829 | T.COM | Target | 2017-11-05 | 2017-11-05 | TSE - Software Engineering
15829 | CRAMER-LI | Withdrawn | 2017-08-13 | 2017-08-13 | TSE - BIOS - Solution Delivery
15829 | TOOLKIT | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - Solution Delivery
15829 | CONNECT | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - Solution Delivery
15829 | OM-FUL | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - Solution Delivery
15829 | NBN-BPM | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15829 | BAMBI | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - Operational Data & Analytics
15829 | B2BGW-NBN | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15829 | LISA-NBN | Target | 2017-08-13 | 2017-08-13 | TSE - Release Management COE
15829 | ISL-FUL | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15829 | WDR | Target | 2017-08-13 | 2017-08-13 | Finance & Strategy - C&P
15829 | T.COM | Withdrawn | 2017-08-13 | 2017-08-13 | TSE - Software Engineering
15829 | SDF | Withdrawn | 2017-08-13 | 2017-08-13 | TSE - Software Engineering
15829 | DB-OOT | Withdrawn | 2017-08-13 | 2017-08-13 | Digital Markets - Digital Prod - Small Business
15829 | LOLIG-NBN | Target | 2017-08-13 | 2017-08-13 | Digital Markets - Digital Prod -Digitisation Wsale
15829 | LOLO | Target | 2017-08-13 | 2017-08-13 | Digital Markets - Digital Prod -Digitisation Wsale
15829 | MAXIM-OBIEE | Target | 2017-08-13 | 2017-08-13 | Cloud Engineering - Core Engineering
15829 | MAXIM | Target | 2017-08-13 | 2017-08-13 | Cloud Engineering - Core Engineering
15829 | CCB-RPRM | Target | 2017-08-13 | 2017-08-13 | TSE - Customer Order Management & Sales
15829 | CCB-RCRM | Target | 2017-08-13 | 2017-08-13 | TSE - Customer Order Management & Sales
15829 | BSL | Withdrawn | 2017-08-13 | 2017-08-13 | TSE - BIOS - Operational Data & Analytics
15829 | ORE-INSIGHT | Withdrawn | 2017-08-13 | 2017-08-13 | TSE - BIOS - Operational Data & Analytics
15829 | B2BGW-MLP | Target | 2017-08-13 | 2017-08-13 | TSE - BIOS - BPM & Integration COE
15800 | CCB-RBILL | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - Billing |  | Functional Infrastructure Test Support
15800 | CCB-OLB | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - Billing |  | Test Support Infrastructure Functional
15800 | PLR | Target | 2017-05-01 | 2018-06-30 | Finance & Strategy BU - GFS |  | Test Support Infrastructure Functional
15800 | CCB-RCRM | Target | 2017-05-01 | 2018-06-30 | TSE - Customer Order Management & Sales |  | Test Support Infrastructure Functional
15800 | MAXIM | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support
15800 | SDF | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support Infrastructure Functional
15800 | CCB-EAI | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - BPM & Integration COE |  | Test Support Infrastructure Functional
15800 | CCB-RIFDI | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - Billing |  | Test Support Infrastructure Functional
15800 | SITEMINDER | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support Infrastructure Functional
15800 | T-DDC | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support Infrastructure Functional
15800 | CCB-RPRM | Target | 2017-05-01 | 2018-06-30 | TSE - Customer Order Management & Sales |  | Test Support Functional
15800 | RETAIL.LIVE | Target | 2017-05-01 | 2018-06-30 | Retail Engagement - Frontline Customer Channels |  | Test Support Infrastructure Functional
15800 | RAA | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support Infrastructure Functional
15800 | MYACCOUNT | Target | 2017-05-01 | 2018-06-30 | TSE - Software Engineering |  | Test Support Infrastructure Functional
15800 | STS | Target | 2017-05-01 | 2018-06-30 | TSE - Customer Order Management & Sales |  | Test Support
15800 | TACBAS | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - Billing |  | Test Support Infrastructure Functional
15800 | FLEXCAB | Target | 2017-05-01 | 2018-06-30 | TSE - BIOS - Billing |  | Test Support Infrastructure Functional
15800 | TIES | Target | 2017-05-01 | 2018-06-30 | Mobility & Collaborations Solutions |  | Test Support Infrastructure Functional
15800 | CCB-COMM | Target | 2017-05-01 | 2018-06-30 | TSE - Customer Order Management & Sales |  | Test Support Infrastructure Functional
15793 | DQR-DAC | Target | 2017-08-31 | 2017-08-31 | TSE - BIOS - Data Alignment
15793 | SFDC | Target | 2017-08-31 | 2017-08-31 | TELSTRA - NON-IT
15781 | MAXIM | Target | 2017-11-12 | 2017-11-12 | TSE - Software Engineering |  | Functional
15781 | OM-FUL | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | ONDB | Withdrawn | 2017-11-12 | 2017-11-12 | TSE - BIOS - Billing |  | Functional
15781 | B2BGW-MLP | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Other
15781 | AM-SHARED1 | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | AXIS | Withdrawn | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | MEDIATOR | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | OM-EAI | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Functional
15781 | EDIS-EAI | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Functional
15781 | EMSBB | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Functional
15781 | NEM-DMS | Target | 2017-11-12 | 2017-11-12 | IP&TE - Application |  | Functional
15781 | BAM | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | WAS | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | UNI-COM | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | SDDB | Target | 2017-11-12 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Functional
15781 | FLEXCAB | Withdrawn | 2017-11-12 | 2017-11-12 | TSE - BIOS - Billing |  | Functional
15781 | DB-OOT | Target | 2017-11-12 | 2017-11-12 | TSE - Software Engineering |  | Functional
15771 | CCB-RCRM | Target | 2017-10-14 | 2017-10-15 | TSE - Customer Order Management & Sales | CRQ000003146765 | Functional
15719 | ITAM | Target | 2017-10-21 | 2017-10-21 | TSE - BIOS - Solution Delivery
15718 | ITAM | Target | 2018-03-17 | 2018-03-17 | TSE - BIOS - Solution Delivery
15701 | PRE-PAID-ACTIVATION | Target | 2017-06-01 | 2017-06-01 | GB2B IT - Corp Functions & Infrastructure Services
15701 | SDF | Target | 2017-09-29 | 2017-09-29 | TSE - Software Engineering
15701 | SERVICE-FEDERATOR | Target | 2017-06-01 | 2017-06-01 | TSE - Software Engineering
15638 | CCB-RCRM | Target | 2018-04-07 | 2018-04-08 | TSE - Customer Order Management & Sales
15638 | ATHENIAN | Target | 2018-04-06 | 2017-10-06 | Media and Marketing
15589 | NPAMS | Target | 2017-02-02 | 2017-02-02 | TSE - BIOS - Solution Delivery
15565 | CCB-RCRM | Target | 2017-11-11 | 2017-11-12 | TSE - Customer Order Management & Sales |  | Functional | Yes
15565 | CCB-RBILL | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Billing |  | Functional
15565 | CCB-PROD-CAT | Target | 2017-11-11 | 2017-11-12 | Digital Markets - Digital Prod - Prodcat |  | Functional
15565 | SDF | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering |  | Functional
15565 | AM-SHARED1 | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Test Support Other
15565 | AXIS | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Test Support Other
15565 | B2BGW-MLP | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
15565 | CCB-PROD-CAT | Target | 2017-08-07 | 2017-11-12 | Digital Markets - Digital Prod - Prodcat |  | Test Support Other
15565 | LISA-BRIGHTSTAR | Target | 2017-08-07 | 2017-11-12 | TSE - Release Management COE |  | Test Support Other
15565 | LISA-NBN | Target | 2017-08-07 | 2017-11-12 | TSE - Release Management COE |  | Test Support Other
15565 | ISL-FUL | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
15565 | FLEXCAB | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Billing |  | Test Support Other
15565 | OM-FUL | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Test Support Other
15565 | CUSTOMER-ADVISORY-TOOL | Target | 2017-08-07 | 2017-11-12 | TSE - Software Engineering |  | Test Support Other
15565 | CUSTOMER-ADVISORY-TOOL | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering |  | Functional
15565 | CCB-RIFDI | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Billing |  | Test Support Other
15565 | CCB-RBILL | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Billing |  | Test Support Other
15565 | T-AAA | Target | 2017-08-07 | 2017-11-12 | IP&TE - Application |  | Other
15565 | OKAPI | Target | 2017-08-07 | 2017-11-12 | Cloud Engineering - Multi Cloud |  | Other
15565 | S&C-EAI | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
15565 | ESQ-SE | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
15565 | NPAMS | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Test Support Other
15565 | UNI-COM | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Billing |  | Test Support Other
15565 | SDF | Target | 2017-08-07 | 2017-11-12 | TSE - Software Engineering |  | Test Support Other
15565 | ONLINE-SHOP | Target | 2017-08-07 | 2017-11-12 | TSE - Software Engineering |  | Test Support Other
15565 | CCB-RCRM | Target | 2017-08-07 | 2017-11-12 | TSE - Customer Order Management & Sales |  | Test Support Other
15565 | B2BGW-NBN | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
15565 | AUTOCAT | Target | 2017-08-07 | 2017-11-12 | TSE - BIOS - Solution Delivery |  | Test Support Other
15565 | T.COM | Target | 2017-11-11 | 2017-11-12 | TSE - Software Engineering |  | Functional
15565 | CCB-RIFDI | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - Billing |  | Functional
15474 | CCB-RCRM | Target | 2017-11-11 | 2017-11-12 | TSE - Customer Order Management & Sales
15474 | CCB-EAI | Target | 2017-11-11 | 2017-11-12 | TSE - BIOS - BPM & Integration COE
15474 | CCB-RPRM | Target | 2017-11-11 | 2017-11-12 | TSE - Customer Order Management & Sales
15390 | ESQ-SE | Target | 2017-12-02 | 2017-12-02 | TSE - BIOS - BPM & Integration COE | CRQ000002645425 | Reference Data
15390 | ISL-FUL | Target | 2017-12-02 | 2017-12-02 | TSE - BIOS - BPM & Integration COE | CRQ000002631785 | Reference Data
15388 | EMSBB | Target | 2017-10-27 | 2017-10-27 | O&SS - BPM & Integration COE - B2B EMS & EAI |  | Other
15388 | ESF-BC | Target | 2017-11-17 | 2017-11-17 | TSE - BIOS - BPM & Integration COE |  | Other
15388 | MQ-HUB | Target | 2017-10-27 | 2017-10-27 | TSE - BIOS - BPM & Integration COE |  | Other
15388 | WIDEFEAS | Target | 2017-11-17 | 2017-11-18 | TSE - BIOS - Solution Delivery |  | Functional
15388 | E-BPM | Target | 2017-11-17 | 2017-11-18 | TSE - BIOS - BPM & Integration COE |  | Functional
15388 | IPAC | Target | 2017-11-16 | 2017-11-17 | TSE - BIOS - Billing |  | Functional
15388 | SFX | Target | 2017-11-17 | 2017-11-17 | TSE - BIOS - BPM & Integration COE |  | Other
15388 | EAST | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery |  | Test Support
15388 | TCSS | Target | 2017-11-16 | 2017-11-17 | Finance & Strategy - C&P |  | Functional
15388 | AMCO | Target | 2017-11-16 | 2017-11-17 | TSE - BIOS - Billing |  | Functional
15370 | CMP | Deployed | 2017-10-02 | 2017-10-02 | TSE - BIOS - Billing | CRQ000003138588 | Functional
15370 | UPS | Withdrawn | 2017-08-19 | 2017-08-19 | TSE - BIOS - Billing
15343 | UCS | Withdrawn | 2017-09-02 | 2017-09-02 | TSE - BIOS - Solution Delivery
15343 | WAS | Withdrawn | 2017-09-30 | 2017-09-30 | TSE - BIOS - Solution Delivery |  | Functional
15343 | UNI-COM | Withdrawn | 2017-06-10 | 2017-06-11 | TSE - BIOS - Solution Delivery |  | Functional
15343 | TBB-OOT | Withdrawn | 2017-09-30 | 2017-09-30 | Digital Markets - Digital Prod - Small Business |  | Functional
15343 | DB-OOT | Withdrawn | 2017-09-30 | 2017-09-30 | Digital Markets - Digital Prod - Small Business |  | Functional
15343 | MAXIM | Confirmed | 2017-09-09 | 2017-09-09 | Cloud Engineering - Core Engineering | CRQ000003080059 | Functional
15343 | OM-FUL | Confirmed | 2017-08-25 | 2017-08-25 | TSE - BIOS - Solution Delivery | CRQ000002727044 | Functional
15343 | SDDB | Target | 2017-08-27 | 2017-08-27 | TSE - BIOS - Solution Delivery |  | Functional
15343 | RAA | Withdrawn | 2017-09-30 | 2017-09-30 | TSE - Software Engineering |  | Functional
15343 | E-BPM | Withdrawn | 2017-09-02 | 2017-09-02 | TSE - BIOS - BPM & Integration COE |  | Functional
15343 | CONNECT | Target | 2017-09-22 | 2017-09-22 | TSE - BIOS - Solution Delivery |  | Functional
15300 | CUSTOMER-ADVISORY-TOOL | Target | 2017-07-21 | 2017-07-21 | TSE - Software Engineering
15300 | MSP | Target | 2017-08-25 | 2017-08-25 | TSE - Software Engineering
15300 | RAA | Target | 2017-07-21 | 2017-07-21 | TSE - Software Engineering
15300 | IPHONE-24X7 | Target | 2017-08-28 | 2017-08-28 | TSE - Software Engineering
15300 | ANDROID-24X7 | Target | 2017-08-28 | 2017-08-28 | TSE - Software Engineering
15263 | CARES | Withdrawn | 2017-05-20 | 2017-05-21 | TELSTRA - NON-IT |  | Functional
15263 | MYACCOUNT | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Software Engineering |  | Functional
15263 | T.COM | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Software Engineering |  | Functional
15263 | SDF | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Software Engineering |  | Test Support
15263 | NPAMS | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - BIOS - Solution Delivery |  | Test Support
15263 | ANDROID-24X7 | Withdrawn | 2017-08-08 | 2017-08-08 | TSE - Software Engineering |  | Functional
15263 | T-DDC | Withdrawn | 2017-09-01 | 2017-09-01 | TSE - Software Engineering |  | Test Support
15263 | OKAPI | Withdrawn | 2017-09-01 | 2017-09-01 | Cloud Engineering - Multi Cloud |  | Test Support
15263 | T-AAA | Confirmed | 2017-09-05 | 2017-09-08 | IP&TE - Application | CRQ000003101298: 07/09-08/09 CRQ000003101306: 05/09-06/09 | Functional
15263 | T-AAA | Withdrawn | 2017-09-19 | 2017-09-19 | IP&TE - Application |  | Functional
15263 | T&DM | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - BIOS - Solution Delivery |  | Test Support
15263 | IPAD-24X7 | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Software Engineering |  | Functional
15263 | IPHONE-24X7 | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Software Engineering |  | Functional
15263 | NDSD | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - BIOS - Solution Delivery |  | Test Support
15263 | XDM | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - BIOS - Solution Delivery |  | Test Support
15263 | SULTAN | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - BIOS - Solution Delivery |  | Test Support
15263 | CCB-RCRM | Withdrawn | 2017-05-20 | 2017-05-21 | TSE - Customer Order Management & Sales |  | Test Support
15233 | EMSBB | Confirmed | 2017-09-08 | 2017-09-09 | TSE - BIOS - BPM & Integration COE | CRQ000003113456
15233 | DB-OOT | Target | 2017-09-09 | 2017-09-09 | TSE - Software Engineering
15233 | IP-RDM | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - Solution Delivery
15233 | CNS-DI | Target | 2017-09-09 | 2017-09-09 | TSE - Software Engineering
15233 | CRAMER-LI | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - Solution Delivery
15233 | MAXIM | Confirmed | 2017-09-09 | 2017-09-09 | TSE - Software Engineering | CRQ000003080059
15215 | CCB-RBILL | Target | 2017-11-10 | 2017-11-12 | TSE - BIOS - Billing
15215 | CCB-RCRM | Target | 2017-11-18 | 2017-11-19 | TSE - Customer Order Management & Sales
15215 | TCM | Target | 2017-11-18 | 2017-11-19 | TSE - Customer Order Management & Sales
15215 | CDBOR | Target | 2017-11-18 | 2017-11-19 | TSE - Customer Order Management & Sales
15215 | FLEXCAB | Target | 2017-11-18 | 2017-11-19 | TSE - Customer Order Management & Sales
15215 | DQR-DAC | Target | 2017-11-10 | 2017-11-12 | TSE - BIOS - Data Alignment
15215 | TCM-EAI | Target | 2017-11-10 | 2017-11-12 | TSE - BIOS - BPM & Integration COE
15215 | CCB-EAI | Target | 2017-11-10 | 2017-11-12 | TSE - BIOS - BPM & Integration COE
15138 | EMSBB | Target | 2017-09-30 | 2017-09-30 | TSE - BIOS - BPM & Integration COE
15138 | CCB-EAI | Withdrawn | 2017-09-23 | 2017-09-23 | TSE - BIOS - BPM & Integration COE
15138 | TCM | Target | 2017-09-30 | 2017-09-30 | TSE - Customer Order Management & Sales | CRQ000003133971
15138 | T-DDC | Target | 2017-10-20 | 2017-10-20 | TSE - Software Engineering
15068 | RAA | Withdrawn | 2017-06-01 | 2017-11-30 | TSE - Software Engineering
15068 | SDDB | Target | 2017-10-01 | 2017-11-30 | TSE - BIOS - Solution Delivery
15068 | TDI-EM | Withdrawn | 2017-06-01 | 2017-11-30 | TSE - Software Engineering
15068 | PMR | Target | 2017-06-01 | 2017-11-30 | Digital Markets - Digital Prod - PMR
15068 | BRIGHTSTAR | Target | 2017-08-01 | 2017-11-06 | TELSTRA - NON-IT
15068 | OKAPI-SSO | Withdrawn | 2017-06-01 | 2017-11-30 | TSE - Software Engineering
15068 | CCB-PROD-CAT | Target | 2017-08-07 | 2017-11-06 | TSE - Customer Order Management & Sales
15068 | SDF | Withdrawn | 2017-05-29 | 2017-11-30 | TSE - Software Engineering
14888 | CCB-PROD-CAT | Target | 2018-02-17 | 2018-02-18 | Digital Markets - Digital Prod - Prodcat
14888 | OM-FUL | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Solution Delivery
14888 | AM-SHARED1 | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Solution Delivery
14888 | CRAMER-LI | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Solution Delivery
14888 | EDW | Target | 2018-02-17 | 2018-02-18 | TSE - BI Delivery
14888 | CCB-RBILL | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Billing
14888 | ISL-FUL | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
14888 | GCM | Target | 2018-02-17 | 2018-02-18 | TSE - Software Engineering
14888 | CMP | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - Billing
14888 | MYACCOUNT | Withdrawn | 2018-02-17 | 2018-02-18 | TSE - Software Engineering
14888 | CCB-EAI | Target | 2018-02-17 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
14771 | NDSD | Target | 2017-08-18 | 2017-08-19 | TSE - BIOS - Solution Delivery |  | Functional
14771 | NICAD-PSTN | Target | 2017-08-18 | 2017-08-18 | TSE - BIOS - Solution Delivery
14771 | NEMO | Target | 2017-08-18 | 2017-08-18 | TSE - BIOS - Solution Delivery
14771 | NSC | Target | 2017-08-11 | 2017-08-11 | TSE - BIOS - Solution Delivery
14771 | LOCATION-MANAGER | Target | 2017-08-11 | 2017-08-11 | TSE - BIOS - Solution Delivery
14771 | MITS | Target | 2017-08-11 | 2017-08-12 | TSE - BIOS - Solution Delivery |  | Functional
14771 | TPD SYSTEM | Target | 2017-08-11 | 2017-08-13 | TSE - BIOS - Solution Delivery |  | Infrastructure Functional Reference Data
14771 | MULTIMAN | Target | 2017-08-11 | 2017-08-12 | TSE - BIOS - Solution Delivery |  | Functional
14771 | NMA | Target | 2017-08-11 | 2017-08-12 | TSE - BIOS - Solution Delivery |  | Functional
14771 | NETINFO | Target | 2017-08-11 | 2017-08-12 | TSE - BIOS - Solution Delivery |  | Functional
14729 | CCB-RCRM | Target | 2018-03-18 | 2018-02-18 | TSE - Customer Order Management & Sales
14729 | BRIGHTSTAR | Target | 2018-02-18 | 2018-02-18 | TELSTRA - NON-IT
14729 | BILL-PAY | Target | 2018-02-18 | 2018-02-18 | Retail Engagement - Billing - Corporate & Payment
14729 | PLR | Target | 2018-02-18 | 2018-02-18 | TELSTRA - NON-IT
14729 | INTEGRALPLUS | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
14729 | EDW | Target | 2018-02-18 | 2018-02-18 | TSE - BI Delivery
14729 | CCB-EAI | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
14729 | SFX | Target | 2018-02-18 | 2018-02-18 | TSE - BIOS - BPM & Integration COE
14729 | SENTINEL | Target | 2018-02-18 | 2018-02-18 | TSE - Software Engineering
14729 | PIMS | Target | 2018-02-18 | 2018-02-18 | Retail Engagement - Frontline Customer Channels
14719 | CONNECT | Target | 2017-08-25 | 2017-08-26 | TSE - BIOS - Solution Delivery | CRQ000003095446
14719 | T&DM | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000002963864
14719 | CONNECT | Target | 2017-08-31 | 2017-08-31 | TSE - BIOS - Solution Delivery
14719 | CONNECT | Target | 2017-08-31 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000003092600
14719 | WFM-WOM | Target | 2017-08-20 | 2017-08-20 | TSE - BIOS - Solution Delivery | CRQ000002991827
14719 | PROMISE | Withdrawn | 2017-08-18 | 2017-08-18 | TSE - BIOS - Solution Delivery | CRQ000003063371
14719 | ITAM | Withdrawn | 2017-05-05 | 2017-09-08 | TSE - BIOS - Solution Delivery
14719 | MAPS4P | Withdrawn | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery
14719 | RNMSERVICES | Target | 2017-06-16 | 2017-06-16 | TSE - Software Engineering
14719 | CRUX | Withdrawn | 2017-07-15 | 2017-09-15 | TSE - BIOS - Solution Delivery
14719 | XDM | Withdrawn | 2017-02-27 | 2017-03-17 | TSE - BIOS - Solution Delivery
14719 | XDM | Withdrawn | 2017-05-05 | 2017-06-26 | TSE - BIOS - Solution Delivery
14719 | PROMISE | Target | 2017-08-25 | 2017-08-26 | TSE - BIOS - Solution Delivery | CRQ000003063371
14719 | WOM-AE | Target | 2017-08-25 | 2017-08-26 | TSE - BIOS - Solution Delivery | CRQ000003096619
14719 | TOMS | Target | 2017-09-01 | 2017-09-01 | TSE - BIOS - Solution Delivery | CRQ000002963533
14719 | TOOLKIT | Withdrawn | 2017-01-20 | 2017-01-21 | TSE - BIOS - Solution Delivery
14695 | TIAS | Confirmed | 2017-09-23 | 2017-09-23 | TSE - BIOS - Billing | CRQ000003095744
14695 | UCS | Target | 2017-09-23 | 2017-09-23 | TSE - BIOS - Solution Delivery | CRQ000003082641
14642 | BILL-PAY | Target | 2017-09-09 | 2017-09-09 | Retail Engagement - Billing - Corporate & Payment
14642 | CCB-OLB | Target | 2017-09-09 | 2017-09-09 | TSE - BIOS - Billing
14600 | CCB-EAI | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE
14600 | CCB-RCRM | Target | 2017-11-05 | 2017-11-05 | TSE - Customer Order Management & Sales
14600 | ISL-FUL | Target | 2017-11-05 | 2017-11-05 | TSE - BIOS - BPM & Integration COE
14468 | DQA | Withdrawn | 2017-08-19 | 2017-08-19 | ITS Platform - BIOS - Data Mgmt COE
14468 | DQR-DAC | Target | 2017-09-19 | 2017-09-19 | TSE - BIOS - Data Alignment
14436 | NBNPLUS-MICROSERVICES | Target | 2016-08-09 | 2016-08-09 | TSE - Software Engineering |  | Functional
14436 | ONLINE-SHOP | Target | 2016-08-30 | 2016-08-31 | TSE - Software Engineering |  | Functional
14436 | SDF | Target | 2016-08-15 | 2016-08-19 | TSE - Software Engineering |  | Functional
14436 | FPD | Target | 2016-08-27 | 2016-08-28 | Retail Engagement - Credit & Fraud |  | Test Support
14436 | CDE | Target | 2016-08-27 | 2016-08-28 | Retail Engagement - Credit & Fraud |  | Test Support
14436 | BILL-PAY | Target | 2016-08-27 | 2016-08-28 | TSE - BIOS - Billing |  | Test Support
14436 | CCB-RCRM | Target | 2016-08-27 | 2016-08-28 | TSE - Customer Order Management & Sales |  | Test Support
14436 | CCB-EAI | Target | 2016-08-27 | 2016-08-28 | TSE - BIOS - BPM & Integration COE |  | Test Support
14405 | AMCO-RASS | Target | 2017-09-30 | 2017-09-30 | TSE - BIOS - Solution Delivery |  | Functional
14405 | TW-QUOTE2ORDER | Target | 2017-09-30 | 2017-09-30 | Digital Markets - Digital Prod -Digitisation Wsale |  | Functional
14234 | RADR-CMS | Target | 2016-08-27 | 2016-08-31 | Retail Engagement - Credit & Fraud |  | Functional
14190 | CCB-RCRM | Target | 2017-11-04 | 2017-11-05 | TSE - Customer Order Management & Sales |  | Functional Test Support | Yes
14190 | CCB-RBILL | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - BIOS - Billing |  | Functional
14190 | PMR | Target | 2017-11-04 | 2017-11-05 | Digital Markets - Digital Prod - PCD |  | Reference Data
14190 | MPM | Target | 2017-03-25 | 2017-03-26 | TSE - BIOS - Solution Delivery |  | Functional
14190 | IPHONE-24X7 | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | MSP | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | ONLINE-SHOP | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Test Support
14190 | UNI-COM | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Solution Delivery |  | Test Support
14190 | CCB-RBILL | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Billing |  | Test Support
14190 | EMSBB | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - BIOS - BPM & Integration COE |  | Test Support
14190 | MICA | Target | 2017-03-25 | 2017-03-26 | TSE - BIOS - Billing |  | Test Support
14190 | AM-MOBILE | Target | 2017-11-28 | 2017-11-28 | Telstra Software Engineering |  | Test Support
14190 | OM-FUL | Target | 2017-03-25 | 2017-03-26 | TSE - BIOS - Solution Delivery |  | Test Support
14190 | ISL-FUL | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - BPM & Integration COE |  | Test Support Other
14190 | CMP | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Billing |  | Test Support
14190 | FLEXCAB | Target | 2017-11-04 | 2017-11-05 | TSE - BIOS - Billing |  | Test Support
14190 | CCB-RCRM | Withdrawn | 2017-11-04 | 2017-11-05 | TSE - Customer Order Management & Sales |  | Test Support
14190 | IPHONE-24X7 | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Test Support
14190 | ANDROID-24X7 | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Test Support
14190 | T.COM | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Test Support
14190 | MYACCOUNT | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Test Support
14190 | CUSTOMER-ADVISORY-TOOL | Target | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | MDUM | Target | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | SDF | Target | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | MYACCOUNT | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | ANDROID-24X7 | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | T.COM | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - Software Engineering |  | Functional
14190 | ISL-FUL | Withdrawn | 2017-03-25 | 2017-03-26 | TSE - BIOS - BPM & Integration COE |  | Other
14190 | CCB-PROD-CAT | Target | 2017-11-04 | 2017-11-05 | Digital Markets - Digital Prod - Prodcat |  | Functional
14151 | AM-SHARED1 | Target | 2016-04-28 | 2016-04-28 | TSE - BIOS - Solution Delivery
13998 | EDW | Target | 2017-06-16 | 2017-06-16 | TSE - BI Delivery
13982 | ARCHIVER | Target | 2017-10-30 | 2017-10-30 | ITS Platform - BIOS - Data Mgmt COE

## Definitions
IR_Number | Definitions.Type | Definitions.Status
17211 | Solution | Not Commenced
17210 | Solution | Not Commenced
17209 | Solution | Not Commenced
17204 | Solution | Not Commenced
17172 | Solution | Not Commenced
17168 | Solution | Not Commenced
17159 | Solution | In Progress
17157 | Solution | Not Commenced
17148 | Solution | Not Commenced
17146 | Solution | Not Commenced
17145 | Solution | Not Commenced
17132 | Solution | Not Commenced
17131 | Solution | Not Commenced
17128 | Solution | Not Commenced
17127 | Solution | Not Commenced
17124 | Solution | Not Commenced
17122 | Solution | Not Commenced
17118 | Solution | Not Commenced
17116 | Solution | Not Commenced
17114 | Solution | Not Commenced
17110 | Solution | Not Commenced
17109 | Solution | Not Commenced
17108 | Solution | Not Commenced
17102 | Solution | Not Commenced
17079 | Solution | In Progress
17076 | Solution | In Progress
17072 | Solution | Not Commenced
17062 | Solution | In Progress
17061 | Solution | Not Commenced
17055 | Solution | Not Commenced
17053 | Solution | Not Commenced
17051 | Solution | Not Commenced
17040 | Solution | Not Commenced
17039 | Solution | Not Commenced
17038 | Solution | Not Commenced
17034 | Solution | Not Commenced
17033 | Solution | Not Commenced
17032 | Solution | Not Commenced
17028 | Solution | Not Commenced
17022 | Solution | Not Commenced
17020 | Solution | Not Commenced
17007 | Solution | In Progress
17005 | Solution | In Progress
17001 | Solution | Not Commenced
17000 | Solution | In Progress
16998 | Solution | In Progress
16997 | Solution | Not Commenced
16995 | Requirements | Not Commenced
16993 | Solution | Not Commenced
16992 | Solution | Not Commenced
16982 | Solution | Not Commenced
16978 | Solution | Not Commenced
16975 | Solution | Not Commenced
16974 | Solution | Not Commenced
16972 | Solution | Complete
16971 | Solution | Not Commenced
16965 | Solution | Complete
16963 | Solution | Complete
16962 | Solution | Not Commenced
16961 | Solution | Complete
16959 | Solution | Complete
16957 | Solution | Not Commenced
16955 | Solution | Complete
16953 | Solution | In Progress
16952 | Solution | Not Commenced
16949 | Solution | In Progress
16948 | Solution | Complete
16945 | Solution | Complete
16944 | Solution | Complete
16943 | Solution | In Progress
16939 | Solution | In Progress
16936 | Solution | Complete
16935 | Solution | Complete
16933 | Solution | In Progress
16930 | Solution | Not Commenced
16926 | Solution | Complete
16915 | Solution | Not Commenced
16911 | Solution | Not Commenced
16910 | Solution | Complete
16909 | Solution | Not Commenced
16906 | Solution | Not Commenced
16902 | Requirements | Not Commenced
16901 | Solution | Complete
16900 | Solution | In Progress
16899 | Solution | Not Commenced
16898 | Solution | Not Commenced
16897 | Solution | Complete
16896 | Solution | Not Commenced
16892 | Solution | In Progress
16890 | Solution | In Progress
16885 | Solution | Not Commenced
16883 | Solution | Not Commenced
16882 | Solution | Complete
16880 | Solution | In Progress
16878 | Solution | In Progress
16877 | Solution | In Progress
16872 | Solution | Not Commenced
16870 | Solution | Not Commenced
16869 | Solution | In Progress
16865 | Solution | Not Commenced
16851 | Solution | Complete
16847 | Solution | In Progress
16845 | Solution | Not Commenced
16841 | Solution | Not Commenced
16841 | Requirements | Complete
16838 | Solution | In Progress
16836 | Solution | Complete
16834 | Solution | Not Commenced
16834 | Requirements | Not Commenced
16830 | Solution | Not Commenced
16827 | Solution | Not Commenced
16820 | Solution | In Progress
16818 | Solution | In Progress
16817 | Solution | In Progress
16816 | Solution | Not Commenced
16812 | Solution | Not Commenced
16809 | Solution | Not Commenced
16808 | Solution | In Progress
16804 | Solution | Not Commenced
16803 | Solution | Not Commenced
16802 | Solution | Not Commenced
16801 | Solution | Not Commenced
16796 | Solution | Complete
16795 | Solution | In Progress
16792 | Solution | Complete
16790 | Solution | Complete
16789 | Solution | In Progress
16782 | Solution | Complete
16780 | Solution | Not Commenced
16778 | Solution | Complete
16774 | Solution | Not Commenced
16773 | Solution | In Progress
16772 | Solution | Not Commenced
16770 | Solution | Not Commenced
16767 | Solution | Not Commenced
16766 | Solution | Not Commenced
16764 | Solution | In Progress
16759 | Solution | Complete
16758 | Solution | Complete
16757 | Solution | Complete
16751 | Solution | In Progress
16750 | Solution | Complete
16747 | Solution | Not Commenced
16727 | Solution | Complete
16714 | Solution | In Progress
16711 | Solution | Not Commenced
16709 | Solution | Not Commenced
16709 | Requirements | Complete
16705 | Solution | Not Commenced
16705 | Requirements | Complete
16704 | Solution | Complete
16703 | Solution | In Progress
16702 | Solution | In Progress
16698 | Solution | Not Commenced
16697 | Solution | In Progress
16695 | Solution | Not Commenced
16687 | Solution | In Progress
16687 | Requirements | Complete
16684 | Solution | Complete
16677 | Solution | Complete
16665 | Solution | Complete
16660 | Solution | Not Commenced
16653 | Solution | Complete
16649 | Solution | Not Commenced
16647 | Solution | Not Commenced
16646 | Solution | Not Commenced
16644 | Solution | Not Commenced
16640 | Solution | Complete
16636 | Solution | Not Commenced
16630 | Solution | In Progress
16627 | Solution | In Progress
16627 | Requirements | Complete
16622 | Solution | Complete
16616 | Solution | In Progress
16615 | Solution | Not Commenced
16612 | Solution | Complete
16609 | Solution | Complete
16607 | Solution | Not Commenced
16606 | Solution | Not Commenced
16605 | Solution | Not Commenced
16600 | Solution | In Progress
16598 | Solution | Complete
16595 | Solution | Complete
16594 | Solution | In Progress
16586 | Solution | In Progress
16579 | Solution | Not Commenced
16578 | Solution | Not Commenced
16574 | Solution | In Progress
16561 | Solution | Complete
16553 | Solution | Complete
16552 | Solution | Complete
16549 | Solution | Complete
16546 | Solution | Not Commenced
16541 | Solution | Not Commenced
16538 | Solution | Not Commenced
16512 | Solution | Not Commenced
16509 | Solution | Not Commenced
16509 | Requirements | Complete
16506 | Solution | Complete
16504 | Solution | Complete
16503 | Solution | Complete
16498 | Solution | Not Commenced
16497 | Solution | Not Commenced
16496 | Solution | Not Commenced
16487 | Solution | Complete
16486 | Solution | Complete
16484 | Solution | Complete
16466 | Solution | Complete
16465 | Solution | Complete
16462 | Solution | In Progress
16457 | Solution | In Progress
16450 | Solution | In Progress
16447 | Solution | In Progress
16443 | Solution | In Progress
16436 | Solution | Complete
16435 | Solution | Not Commenced
16433 | Solution | Complete
16431 | Solution | In Progress
16430 | Solution | In Progress
16427 | Solution | In Progress
16416 | Solution | In Progress
16414 | Solution | In Progress
16400 | Solution | Complete
16391 | Solution | Not Commenced
16390 | Solution | Complete
16386 | Solution | Not Commenced
16381 | Solution | In Progress
16379 | Solution | In Progress
16378 | Solution | In Progress
16363 | Solution | In Progress
16360 | Solution | Complete
16342 | Solution | Complete
16339 | Solution | In Progress
16322 | Solution | Complete
16313 | Solution | Not Commenced
16311 | Solution | Complete
16306 | Solution | Not Commenced
16305 | Solution | Complete
16301 | Solution | Complete
16289 | Solution | In Progress
16281 | Solution | Not Commenced
16274 | Solution | In Progress
16272 | Solution | Not Commenced
16265 | Solution | Complete
16243 | Solution | Not Commenced
16240 | Requirements | Not Commenced
16232 | Solution | In Progress
16230 | Solution | Complete
16207 | Solution | Complete
16202 | Solution | In Progress
16193 | Solution | Not Commenced
16192 | Solution | In Progress
16192 | Requirements | Complete
16185 | Solution | Not Commenced
16175 | Solution | Not Commenced
16131 | Solution | Complete
16130 | Solution | Complete
16119 | Solution | Complete
16114 | Solution | Not Commenced
16113 | Solution | Not Commenced
16109 | Solution | Complete
16107 | Solution | Not Commenced
16101 | Solution | Complete
16094 | Solution | Not Commenced
16078 | Solution | In Progress
16077 | Solution | In Progress
16069 | Solution | Complete
16060 | Solution | In Progress
16056 | Solution | Not Commenced
16046 | Solution | Complete
16039 | Solution | Complete
16006 | Solution | In Progress
16005 | Solution | Complete
15945 | Solution | In Progress
15944 | Solution | Complete
15937 | Solution | Complete
15923 | Solution | Complete
15915 | Solution | In Progress
15913 | Solution | Complete
15882 | Solution | Complete
15868 | Solution | Complete
15843 | Solution | Complete
15832 | Solution | Not Commenced
15829 | Solution | Complete
15800 | Solution | In Progress
15793 | Solution | Not Commenced
15781 | Solution | Complete
15771 | Solution | Complete
15736 | Solution | Not Commenced
15719 | Solution | Not Commenced
15718 | Solution | In Progress
15717 | Solution | Not Commenced
15701 | Solution | In Progress
15638 | Solution | In Progress
15589 | Requirements | Not Commenced
15565 | Solution | Complete
15482 | Solution | In Progress
15474 | Solution | Complete
15390 | Solution | Complete
15388 | Solution | In Progress
15383 | Solution | Not Commenced
15370 | Solution | Complete
15343 | Solution | Complete
15300 | Solution | In Progress
15263 | Solution | Complete
15233 | Solution | Complete
15215 | Solution | Complete
15140 | Solution | Not Commenced
15139 | Solution | Not Commenced
15138 | Solution | In Progress
15068 | Solution | Complete
14954 | Solution | Not Commenced
14888 | Solution | Complete
14771 | Solution | Complete
14729 | Solution | Complete
14719 | Solution | In Progress
14695 | Solution | Complete
14642 | Solution | In Progress
14600 | Solution | Complete
14526 | Solution | Not Commenced
14526 | Requirements | Complete
14468 | Solution | Complete
14436 | Solution | Complete
14405 | Solution | In Progress
14358 | Solution | In Progress
14190 | Solution | Complete
14151 | Solution | Complete
14077 | Solution | Not Commenced
13998 | Solution | Not Commenced
13982 | Solution | In Progress

## ChildIRs
IR_Number | ChildIR.IR_Number
17053 | 16579
17051 | 17158
17048 | 16750
17005 | 15945
16993 | 17063
16993 | 17066
16993 | 17103
16959 | 17018
16939 | 15068
16930 | 17064
16923 | 16766
16906 | 15250
16906 | 16504
16898 | 16586
16882 | 16934
16862 | 15522
16851 | 16956
16851 | 16977
16851 | 17019
16820 | 15007
16818 | 17022
16808 | 16409
16782 | 16954
16766 | 16614
16766 | 16766
16764 | 16767
16684 | 16574
16630 | 17002
16616 | 16803
16609 | 16919
16609 | 16966
16574 | 15756
16574 | 16093
16504 | 17076
16503 | 17226
16497 | 16496
16487 | 16665
16486 | 16697
16466 | 16649
16443 | 15767
16433 | 16971
16431 | 16635
16202 | 16990
16109 | 16801
15829 | 16436
15829 | 16730
15829 | 17132
15781 | 16666
15781 | 16730
15717 | 15718
15717 | 15719
15717 | 15720
15701 | 16794
15474 | 17105
15343 | 16973
15343 | 17079
15233 | 15445
15140 | 14989
15140 | 15138
15138 | 14989
15068 | 16939
14888 | 17024
14771 | 15429
14771 | 15433
14771 | 15435
14729 | 16711
14719 | 16669
14719 | 16725
14719 | 16728
14642 | 15198
14642 | 15847
14642 | 16280
14642 | 16401
14642 | 16693
14642 | 16946
14642 | 17140
14600 | 16732
14526 | 15968
14526 | 16982
14526 | 17107
14468 | 15897
14468 | 16208
14468 | 16410
14436 | 14992

## ParentIRs
IR_Number | ParentIR.IR_Number
17226 | 16503
17158 | 17051
17140 | 14642
17132 | 15829
17079 | 15343
17076 | 16504
17038 | 14102
17024 | 14888
17022 | 16818
17019 | 16851
17018 | 16959
17002 | 16630
16994 | 16510
16982 | 14526
16980 | 16316
16977 | 16851
16973 | 15343
16971 | 16433
16966 | 16609
16956 | 16851
16954 | 16782
16946 | 14642
16939 | 15068
16934 | 16882
16919 | 16609
16803 | 16616
16801 | 16109
16789 | 17037
16767 | 16764
16766 | 15828
16766 | 16766
16766 | 16923
16766 | 17141
16765 | 15941
16750 | 17048
16730 | 15781
16730 | 15829
16711 | 14729
16697 | 16486
16693 | 14642
16666 | 15781
16665 | 16487
16660 | 16591
16653 | 14974
16649 | 16466
16586 | 16898
16579 | 17053
16578 | 13952
16574 | 16684
16504 | 15250
16504 | 16906
16496 | 16497
16465 | 15626
16436 | 15829
16390 | 15250
16301 | 14497
16265 | 14497
15945 | 17005
15719 | 15717
15718 | 15717
15370 | 11086
15370 | 14198
15138 | 15140
15068 | 16939
14719 | 14697
14719 | 16007
14436 | 13583
14405 | 9633
14234 | 12944
13982 | 10630

## TICRFieldMapping (hidden)
TICR Field Label | TICR Field Name | Field Name in Plutora | Date
IR# | IR_Number | IR #
Current Planned Release | Release_Rollup | Release Name
Title | Title | IR Name
IT Project Manager | IT_Project_Manager_Name | Project Manager
Description | Description | Description
Description of Problem | Description_Of_Problem | Description of Problem
Description of Impact | Description_Of_Impact | Description of Impact
Deployment category | Deployment_Category | Deployment category
Deployment details | Deployment_Details | N/A | removed 05/09/14
Functional Categorisation | Functional_Category | Functional Area Business Impact
Aggregated Risk Rating | Risk_Rating | Aggregated Risk Rating | removed 05/09/14
Description of Risk | Risk_Description | Risk Description | removed 05/09/14
Backout / Mitigation Strategy | Risk_Strategy | IR Backout / Mitigation Strategy | removed 05/09/14
Overall SI/High Classification | SI_Classification | IR Classification | removed 05/09/14
SI component | SI_Component | SI component | removed 05/09/14
High component | High_Component | High component | removed 05/09/14
Test Support IR | Test_Support_IR | Test Support IR
State | State | State
Type | Type | IR Delivery Type
Category | Category | IR Category
Funding - Funding Confirmed | DCP2_Funding | Funding - Funding Confirmed
Deploying Indep, requiring CAT | Indep_Requiring_CAT_Rls | Deploying Indep, requiring CAT
Requirements Lead | RequirementsLead_fullname | Requirements Lead
EPM Owner (Business Sponsor) | EPM_Owner_fullname | EPM Owner (Business Sponsor)
Actual Cost $ | IR_Actual_Cost | Actual IR Cost ($)
Business Priority | Business_Priority | Business Priority
Customer Segments | Customer_Segments | Customer Segments
Planned Implementation Date | Date_Required
Endorsed/Actual Impl. Date | Implemented Date
IT Project Manager Area | IT_Project_Manager_Area |  | Added 24/03/14
EPM Project Manager Area | EPM Project Manager Area |  | Added 24/03/14
EMP Project Manager | EPM_Proj_Manager_fullname |  | Added 07/04/14
Requirements Received Date | Reqs_Received_Date |  | Added 01/09/14
SID/SAD Received Date | SIDSAD_Received_Date |  | Added 01/09/14
Director Endorsed Total | DIRECTOR_ENDORSED_TOTAL <this is a calculated field> | Planned IR Cost ($)
Business Drivers - Type | Business_Driver.Category_Type | 1) Legal / Regulatory Commitment 2) Legal / Regulatory Commitment Details 3) Marketing Campaign 4) Marketing Campaign 5) Compliance with 3rd Party 6) Compliance with 3rd Party 7) Operational Improvements 8) Operational Improvements 9) Other 10) Other
Business Drivers - Description | Business_Driver.Description | Business Event Associated (Details)
Operational Impacts: Type | Operational_Impacts.Category_Type | Operational Impacts: Billing and Collections
Operational Impacts: Description | Operational_Impacts.Description | Operational Impacts: Capacity Stability
Associated Dependencies - Dependency Type | Dependencies.Dependency_Type | Solution Dependencies (Yes/No)
Associated Dependencies - IR# | Dependencies.DependantIR.IR_Number | Solution Dependencies (IR#)
Associated Dependencies - Description | Dependencies.Description | Solution Dependencies (Details)
Production Activity - Application | Deployment_Activities.Application | Application
Production Activity - Status | Deployment_Activities.Status | Deployment Status
Production Activity - Change Start Date | Deployment_Activities.Change_Start_Date | Change Start Date
Production Activity - Change End Date | Deployment_Activities.Change_End_Date | Change End Date
Production Activity - Workstream | Deployment_Activities.Workstream | Workstream
Production Activity - CRQ | Deployment_Activities.CRQ_id | CRQ
Delivers Business Value | Deployment_Activities.Delivered_Businesss_Value
IR# | IR_Number
Type | Definitions.Type
Status | Definitions.Status
Requirements Received | Definitions.Requirements_Received |  | removed 18/08/14
SID/SAD Received | Definitions.SID_SAD_Received |  | removed 18/08/14
Associated Child IRs | ChildIR | Related Child IR's
Associated Parent IRS | ParentIR | Related Parent IR's
IR
Business Drivers
Operational Impacts
Dependencies
Deployment Activites
Child IRs
Parent IRs
Business Drivers
Business Drivers
Operational Impacts
Operational Impacts
Dependencies
Dependencies
Deployment Activites
Deployment Activites
Child IRs
Child IRs
Parent IRs
Parent IRs
Parent IRs
Parent IRs
Definitions