## IR_Data
IR_Number | Release_Rollup | Title | IT_Project_Manager_Name | Description | Description_Of_Problem | Description_Of_Impact | Deployment_Category | Functional_Category | Test_Support_IR | State | Type | Category | DCP2_Funding | Indep_Requiring_CAT_Rls | RequirementsLead_fullname | EPM_Owner_fullname | IR_Actual_Cost | Business_Priority | Customer_Segments | Date_Required | Implemented_Date | IT_Project_Manager_Area | EPM_Project_Manager_Area | EPM_Proj_Manager_fullname | Date_Reqs_Received | Date_Reqs_Completed | Date_Solution_Completed | Date_Funding_In_Place | Date_Moved_to_IT_Endorsed | Date_Moved_to_Implemented | Requirements_Lead_Area | EPM_Owner_Area | financial_oom | IT_Project_Manager.email
33356 | R1702 | A.46022652 STOA Spillover | New User999 | Capabilities to enable SIP Connect services to be deployed over non-NBN Telstra Broadband Accesses. The scope will be to enable the following: - Completion of LOLO-NBN functionality spilling over from R1611 | Business Broadband is a high growth product requiring enhancements to increase competitiveness and improve customer experience. | Completion of testing for functionality development for SIP Trunking over Broadband product. |  | Activation Assurance Billing & Credit Online Products | No | Solution | TDP | Cat-3A | No |  | Scarlett Lin | Crispin Blackall |  |  | Wholesale | 2017-02-12 |  | GB2B IT - Concept to Market & Mobility | TO - Networks | Barbara Matoe | 2016-10-03 |  | 2016-12-22 16:23 |  | 2016-12-23 09:26 |  | TO - Networks | GES - Global Products & Services | 2393689 | newuser999a@gmail.com
23456 | R1702 | A-46050107 CAT - Pre Paid Activations | Priya Chandrashekar | Siebel mastered customers (Consumers, Sole Traders) with or without existing prepaid mobile service will be able to activate prepaid service (Mobile, Tablet, WBB) using Customer Advisory Tool. Proposed solution will allow Siebel customers to activate prepaid services by calling FOH or visiting retail store. FOH consultant will be able to view existing post-paid or prepaid services, create new service and perform port-in orders using CAT. The intention is to offer integrated experience and clear call to action for activating prepaid pre-allocated mobile number. Proposed solution will also offer document verification check functionality, port-in service and mobile registration capabilities by calling microservices to interact with existing downstream systems and its interfaces that are delivered as part of Online Pre-Paid Activation (PPA) and ACMA Projects. | Overview: Siebel mastered customers (Consumers, Sole Traders) with or without existing prepaid mobile service will be able to activate prepaid service (Mobile, Tablet, WBB) using Customer Advisory Tool. Proposed solution will allow Siebel customers to activate prepaid services by calling FOH or visiting retail store. FOH consultant will be able to view existing post-paid or prepaid services, create new service and perform port-in orders using CAT. The intention is to offer integrated experience and clear call to action for activating prepaid pre-allocated mobile number. Proposed solution will also offer document verification check functionality, port-in service and mobile registration capabilities by calling microservices to interact with existing downstream systems and its interfaces that are delivered as part of Online Pre-Paid Activation (PPA) and ACMA Projects. | - Engage in meaningful conversation with the customer from the outset - Understand and service the customer needs - Provide the right advice to the customer - Share customer learnings easily with all agents |  | Online | No | Solution | Agile | Cat-3A | Yes |  | Huw Fowles | Troy Chandler |  |  | Business | 2017-02-12 |  | Digital Markets - Digital Channels | TR - Telstra Consumer | Bryan Dunne | 2016-05-16 |  | 2017-01-27 11:19 | 2016-12-23 09:03 | 2016-12-23 09:02 |  | TR - Telstra Consumer | TR - Telstra Digital | 350413 | priya.chandrashekar@plutora.com
98765 | R1702 | A-46050107 CAT - Pre Paid Activations | new user | Siebel mastered customers (Consumers, Sole Traders) with or without existing prepaid mobile service will be able to activate prepaid service (Mobile, Tablet, WBB) using Customer Advisory Tool. Proposed solution will allow Siebel customers to activate prepaid services by calling FOH or visiting retail store. FOH consultant will be able to view existing post-paid or prepaid services, create new service and perform port-in orders using CAT. The intention is to offer integrated experience and clear call to action for activating prepaid pre-allocated mobile number. Proposed solution will also offer document verification check functionality, port-in service and mobile registration capabilities by calling microservices to interact with existing downstream systems and its interfaces that are delivered as part of Online Pre-Paid Activation (PPA) and ACMA Projects. | Overview: Siebel mastered customers (Consumers, Sole Traders) with or without existing prepaid mobile service will be able to activate prepaid service (Mobile, Tablet, WBB) using Customer Advisory Tool. Proposed solution will allow Siebel customers to activate prepaid services by calling FOH or visiting retail store. FOH consultant will be able to view existing post-paid or prepaid services, create new service and perform port-in orders using CAT. The intention is to offer integrated experience and clear call to action for activating prepaid pre-allocated mobile number. Proposed solution will also offer document verification check functionality, port-in service and mobile registration capabilities by calling microservices to interact with existing downstream systems and its interfaces that are delivered as part of Online Pre-Paid Activation (PPA) and ACMA Projects. | - Engage in meaningful conversation with the customer from the outset - Understand and service the customer needs - Provide the right advice to the customer - Share customer learnings easily with all agents |  | Online | No | Solution | Agile | Cat-3A | Yes |  | Huw Fowles | Troy Chandler |  |  | Business | 2017-02-12 |  | Digital Markets - Digital Channels | TR - Telstra Consumer | Bryan Dunne | 2016-05-16 |  | 2017-01-27 11:19 | 2016-12-23 09:03 | 2016-12-23 09:02 |  | TR - Telstra Consumer | TR - Telstra Digital | 350413 | newuser@plutora.com

## BusinessDrivers
IR_of_Business_Driver.IR_Number | Category_Type | Description | Planned_Date

## Dependencies
ParentIR.IR_Number | Dependency_Type | DependantIR.IR_Number | Description

## DeployActivities
IR.IR_Number | Application | Status | Change_Start_Date | Change_End_Date | Workstream | CRQ_id | Activity_Type

## Definitions
IR.IR_Number | Type | Status

## ChildIRs
IR_Number | ChildIR.IR_Number
15607 | 15750
15590 | 14491
15439 | 15817
15231 | 15639
15013 | 14509
14468 | 15897
14090 | 15929

## ParentIRs
IR_Number | ParentIR.IR_Number
15932 | 15903
15929 | 14090
15927 | 15796
15918 | 15893
15917 | 15895
15911 | 15759
15862 | 14149
15847 | 14642
15817 | 15439
15590 | 13380
15013 | 14908
14198 | 11086
14090 | 14911